## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Work Order for Laying Distribution Pipeline (PART-2) & Providing FHTC (PART-2) of Ichapur PWSS at J.B. PUR Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | JE/RWS/Jagatballavpur,JE/RWS/Panchla | ORD/000021/2023-2024 | 1674/HD | 19/04/2023 | 18/06/2023 | PIKASU BOSE | 149.08 | 44.99 | 30.18 | 60
2 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Ichhapur PWSS (Mouza-Ichhapur, Ranmahal & Tripurapur) of Jagatballavpur Block under Howrah Division PHE Dte. | AE/SADAR | JE Sadar | ORD/000073/2022-2023 | 1016/HD | 05/05/2022 | 20/05/2022 | ENVIROTECH SOLUTIONS | 3.04 | 3.04 | 100 | 0
3 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Piped Water Supply Schemes in different Blocks in the District of Howrah under Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000111/2024-2025 | 3730/HD | 29/08/2024 | 28/09/2024 | HORIZEN | 4.93 | 2.2 | 44.68 | 0
4 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Continuation order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Ichapur PWSS of Jagatballavpur Block of Howrah Sadar Sub Division Sub-Division under Howrah Division, P.H.E. Dte. | AE/SADAR | JE/RWS/Panchla | ORD/000314/2023-2024 | 4254/HD | 28/11/2023 | 28/12/2023 | AUXILIARY TUBEWELL DRILLERS | 25.64 | 12.17 | 47.47 | 100
5 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Construction of Concrete road for movement of vehicle for construction of Over Head reservoir site (PH 1) at Ichapur PWSS under Jagatballavpur Block under Howrah Sadar Sub Division, P.H.E. Dte. | AE/SADAR | JE/RWS/Panchla | ORD/000658/2023-2024 | 1298/HD | 13/03/2024 | 27/04/2024 | RANI CONSTRUCTION | 11.27 | 0 | 0 | 0
6 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Ichapur PWSS of Jagatballavpur Block of Howrah Sadar Sub Division Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR |  | ORD/000694/2022-2023 | 312/HD | 20/01/2023 | 19/02/2023 | ALLIED TUBEWELLS PRIVATE LIMITED | 25.64 | 0 | 0 | 0
7 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Work Order for Construction of 2 nos Pump House ( 5.40m x 3.60 m), 2nos Construction of Boundary Walls, Rising Main Pipeline Work, Laying Distribution Pipeline (Part-1) & Providing FHTC(Part-1) of Ichapur PWSS at J.B. PUR Block of Howrah District under Howrah Division,PHE DTE (PART-I) | AE/SADAR | JE/RWS/Panchla | ORD/000796/2022-2023 | 977/HD | 10/03/2023 | 06/09/2023 | D D CONSTRUCTION | 110.53 | 0 | 0 | 0
8 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Work Order for Construction of 200 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/4/2012) including Soil Investigation, Foundation Design & All pipe Connection For Ichapur PWSS at J.B. PUR Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | JE/RWS/Panchla | ORD/000870/2022-2023 | 1347/HD | 27/03/2023 | 21/01/2024 | RANI CONSTRUCTION | 91.61 | 8.23 | 8.99 | 10
9 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Material Requisition To Resource Division |  |  | RTOR000051/2022-2023 | 2839/HD | 23/12/2022 |  | Resource Division | 12.32 | 0 | 0 | 0
10 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Material Requisition To Resource Division |  |  | RTOR000077/2022-2023 | 446/HD | 06/02/2023 |  | Resource Division | 12.27 | 0 | 0 | 0
11 | HOWRAH | Jagatballavpur | Howrah Division | ICHAPUR PWSS | SM/13629 | New | Material Requisition To Resource Division |  |  | RTOR000116/2023-2024 | 1317/HD | 14/03/2024 |  | Resource Division | 17.52 | 0 | 0 | 0
12 | HOWRAH | Jagatballavpur | Electrical | ICHAPUR PWSS | SM/13629 | New | Adhoc payment to WBSEDCL against service connnection |  |  | BILL/01127/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 109.23 | 0 | 0 | 0
13 | HOWRAH | Jagatballavpur | Electrical | ICHAPUR PWSS | SM/13629 | New | Quotation Money deposition for new service connection at Ichapur pwss, P.H No.-I , Dist-Howrah under ED PHED. Application No.- 1007513772 Ref. ID- 106460039 |  |  | BILL/06102/2023-2024 | 761 | 16/02/2024 |  | WBSEDCL | 17.39 | 0 | 0 | null
14 | HOWRAH | Jagatballavpur | Electrical | ICHAPUR PWSS | SM/13629 | New | Quotation money deposition for new service connection at Ichhapur pwss , P.H No.-II, Dist-Howrah under PHED. App. No.-1007566560 Ref.ID: 106496241 SM/13629 |  |  | BILL/06259/2023-2024 | 859 | 11/03/2024 |  | WBSEDCL | 17.26 | 0 | 0 | null
15 | HOWRAH | Jagatballavpur | Electrical | ICHAPUR PWSS | SM/13629 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ichapur water supply scheme, T.W. No.- I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000127/2022-2023 | 3541/ED | 30/12/2022 | 30/03/2023 | KASHINATH PAL & CO. | 21.15 | 0 | 0 | 0
Total | [13 empty] | 628.89 | 70.64 | 11.23