## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Udaynarayanpur | Howrah Division | Sibpur Piped Water Supply Scheme. | SM/13769 | New | Work Order for Sinking of 2nos 250 X 150mm dia Tube Well 230 mtr,Construction of 2nos Pump House cum switch room with sanitary arrangement, Laying Distribution system (LDS) with necessaery inter-connections with OHR and bypass arrangemnet etc. all complete, Functional Household Tap Connection (FHTC) works, Construction of 200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (Drawing No-PC-I/O.H.R/9/2012) with necessary soil investigation with foundation design as per soil test report For SIBPUR PWSS at Udaynarayanpur Block under uluberia Sub Division under Howrah Division, P. H. E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000020/2023-2024 | 1652/HD | 18/04/2023 | 17/04/2024 | SANJOY GHOSH | 328.49 | 99.49 | 30.29 | 55
2 | HOWRAH | Udaynarayanpur | Howrah Division | Sibpur Piped Water Supply Scheme. | SM/13769 | New | Construction of Boundary Wall, Construction of Approach Road and Land Development at HEAD WORK Site and 2nd Tube Well Site of SHIBPUR Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte. | AE/RWS |  | ORD/000044/2024-2025 | 2888/HD | 25/06/2024 | 24/08/2024 | SANJOY GHOSH | 62.98 | 0 | 0 | 0
3 | HOWRAH | Udaynarayanpur | Howrah Division | Sibpur Piped Water Supply Scheme. | SM/13769 | New | Rising Main & Inter Connection with both tube wells of SIBPUR PWSS in Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS |  | ORD/000076/2024-2025 | 3166/HD | 12/07/2024 | 11/08/2024 | TIYASA ENTERPRISE | 5.17 | 0 | 0 | 0
4 | HOWRAH | Udaynarayanpur | Howrah Division | Sibpur Piped Water Supply Scheme. | SM/13769 | New | Work Order for Preparation of DPR for new piped water supply scheme of Sibpur PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu |  | ORD/000451/2021-2022 | 252/HD | 07/02/2022 | 22/02/2022 | APEX ENGINEERING | 2.7 | 2.7 | 100 | 100
5 | HOWRAH | Udaynarayanpur | Howrah Division | Sibpur Piped Water Supply Scheme. | SM/13769 | New | Material Requisition To Resource Division |  |  | RTOR000050/2023-2024 | 3217/HD | 05/09/2023 |  | Resource Division | 14.7 | 0 | 0 | 0
6 | HOWRAH | Udaynarayanpur | Howrah Division | Sibpur Piped Water Supply Scheme. | SM/13769 | New | Material Requisition To Resource Division |  |  | RTOR000109/2023-2024 | 1049/HD | 04/03/2024 |  | Resource Division | 0.83 | 0 | 0 | 0
7 | HOWRAH | Udaynarayanpur | Electrical | Sibpur Piped Water Supply Scheme. | SM/13769 | New | Adhoc Payment to WBSEDCL against service Connection |  |  | BILL/01126/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 117.51 | 0 | 0 | 0
8 | HOWRAH | Udaynarayanpur | Electrical | Sibpur Piped Water Supply Scheme. | SM/13769 | New | Quotation bill for new service connection charge for Shibpur PWSS TW - I |  |  | BILL/04436/2023-2024 | 496 | 07/12/2023 |  | WBSEDCL | 12.3 | 0 | 0 | 0
9 | HOWRAH | Udaynarayanpur | Electrical | Sibpur Piped Water Supply Scheme. | SM/13769 | New | Quotation Bill for New Service Connection at Sibpur W/S. Sch. PH-II |  |  | BILL/04438/2023-2024 | 511 | 08/12/2023 |  | WBSEDCL | 10.12 | 0 | 0 | 0
10 | HOWRAH | Udaynarayanpur | Electrical | Sibpur Piped Water Supply Scheme. | SM/13769 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sibpur water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000258/2022-2023 | 925/ED | 22/02/2023 | 23/05/2023 | ESENCE ENGINEERING CONCERN | 21.35 | 10.29 | 48.22 | 90
Total | [13 empty] | 576.15 | 112.48 | 19.52