## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Jagatballavpur | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Laying distribution system (LDS) of existing drawing for 225 mm dia from (Node point J127-J488), for 200 mm dia (Node point J136-J144), for 180 mm dia (Node point J144-J148), for 160 mm dia (Node point J148-J508 & J10-J17), for 140 mm dia (Node point J152-J510 & J10-J01), for 125 mm dia (Node point J160-J167 & J17-J21), for 110 mm dia (Node point J17-J552), for 90 mm dia (Node point J330-J187) with 712 nos. Functional household tap connection (FHTC) and aproach road with land development at 2nd tube well site & allied works of Nimabalia PWSS at J.B. Pur Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division PHE Dte. (SM/13770) | AE/SADAR | je_how_rws_jagat | ORD/000025/2024-2025 | 2820/HD | 20/06/2024 | 19/08/2024 | GHOSH ENTERPRISE | 127.58 | 38.07 | 29.84 | 40
2 | HOWRAH | Jagatballavpur | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Work Order for Construction Of 300 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/11/2012) Including All pipe Connection For Augmentation Of Nimabalia PWSS at Jagatballavpur Block Of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000028/2023-2024 | 1697/HD | 21/04/2023 | 15/02/2024 | RAYCON CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 121.92 | 15.05 | 12.35 | 10
3 | HOWRAH | Jagatballavpur | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Land Development at OHR site & allied works at Nimabalia PWSS of J.B.Pur Block under Howrah Sadar Sub-Division under Howrah Division, PHE Dte. | AE/SADAR | je_how_rws_jagat | ORD/000033/2024-2025 | 640/HSSD | 25/06/2024 | 25/07/2024 | TRADE GREEN | 4.8 | 2.4 | 49.98 | 100
4 | HOWRAH | Jagatballavpur | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Work Order for Construction of Culvert & Approach Road at Nimabalia OHR Site under Nimabalia PWSS in J.B Pur Block under Howrah Division PHE Dte. Howrah. | AE/SADAR |  | ORD/000071/2023-2024 | 1932/HD | 10/05/2023 | 09/07/2023 | TRADE GREEN | 7.11 | 7.11 | 99.97 | 100
5 | HOWRAH | Jagatballavpur | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Nimabalia PWSS (Mouza-Moulagachhi, Finga Gachhi, Marghurali & Nimabalia) of Jagatballavpur Block under Howrah Division PHE Dte. | AE/SADAR | JE Sadar | ORD/000074/2022-2023 | 1017/HD | 05/05/2022 | 20/05/2022 | ENVIROTECH SOLUTIONS | 3.31 | 3.31 | 100 | 100
6 | HOWRAH | Jagatballavpur | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Construction of 2 Nos. Pump House (5.40m x 3.60 m) at 1st & 2nd Tube Well Sites Construction of Boundary Wall at 1st Tube Well Site, Construction of Boundary Wall at 2nd Tube Well Site, Laying Distribution Pipeline, providing Functional Household Tap Connection(FHTC) & Rising Main Pipeline Work From 2nd Pump House to 1st Pump House & OHR for NIMABALIA PWSS at J.B. PUR Block of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC=850] | AE/SADAR | je_how_rws_jagat | ORD/000200/2023-2024 | 3257/HD | 11/09/2023 | 09/03/2024 | GHOSH ENTERPRISE. | 175.9 | 87.27 | 49.61 | 60
7 | HOWRAH | Jagatballavpur | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Nimabalia PWSS of Jagatballavpur Block of Howrah Sadar Sub Division Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | JE Sadar | ORD/000695/2022-2023 | 313/HD | 20/01/2023 | 19/02/2023 | R CONSTRUCTION | 25.64 | 25.52 | 99.51 | 100
8 | HOWRAH | Jagatballavpur | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 135/HD | 10/01/2024 |  | Resource Division | 15.21 | 0 | 0 | 0
9 | HOWRAH | Jagatballavpur | Howrah Division | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Material Requisition To Resource Division |  |  | RTOR000078/2022-2023 | 446/HD | 06/02/2023 |  | Resource Division | 18.43 | 0 | 0 | 0
10 | HOWRAH | Jagatballavpur | Electrical | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Quotation Bill for New Service Connection at Nimabalia W/S. Sch. PH-2 |  |  | BILL/00020/2023-2024 | 04 | 13/04/2023 |  | WBSEDCL | 3.17 | 0 | 0 | 0
11 | HOWRAH | Jagatballavpur | Electrical | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Additional quotation money deposit for Nimabalia w/s scheme. P.H-I, dist-howrah under ED/PHED. |  |  | BILL/00747/2023-2024 | 35 | 12/05/2023 |  | WBSEDCL | 3.97 | 0 | 0 | 0
12 | HOWRAH | Jagatballavpur | Electrical | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Quotation Bill for New Service Connection at Nimabalia W/S. Sch. PH-I |  |  | BILL/01298/2022-2023 | 189 | 16/03/2023 |  | WBSEDCL | 7.62 | 0 | 0 | 0
13 | HOWRAH | Jagatballavpur | Electrical | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Quotation money deposition for shifting of L.T O.H along with service cable at Nimabalia P.H No-I , Dist-Howrah under ED PHED. App. No.-100000101729 Ref I.D : 860293289 SM/13770 |  |  | BILL/06282/2023-2024 | 879 | 13/03/2024 |  | WBSEDCL | 0.63 | 0 | 0 | null
14 | HOWRAH | Jagatballavpur | Electrical | Nimabalia Piped Water Supply Scheme, Block-Jagatballavpur, Dist- Howrah. | SM/13770 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nimabalia water supply scheme, T.W. No.- I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000119/2022-2023 | 3544/ED | 30/12/2022 | 30/03/2023 | GHOSE ENGINEERING SYNDICATE | 22.59 | 10.83 | 47.95 | 75
Total | [13 empty] | 537.88 | 189.56 | 35.24