## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Bagnan - I | Howrah Division | Patinan Piped Water Supply Scheme | SM/13848 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells (Part-A) & Construction of Swtich Room with Sanitary and water Supply arrangement at Head Work Site and Construction of 250 cum. capacity 20 mtr staging height RCC Over Head Reservoir (Drawing No:PC-I/OHR/10/2012) including Pipe connection & soil investigation and design at PATINAN PWSS OF BAGNAN-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | AE/Ulu | JE/USD | ORD/000008/2023-2024 | 1553/HD | 05/04/2023 | 04/04/2024 | SADHURHAT CO OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 217.39 | 88.39 | 40.66 | 32
2 | HOWRAH | Bagnan - I | Howrah Division | Patinan Piped Water Supply Scheme | SM/13848 | New | Preparation of DPR for Patinan PWSS, Bagnan-I Block under Uluberia Sub-division of Howrah Division P.H.E Dte. | AE/Ulu | JE-USD | ORD/000365/2022-2023 | 460/AE/USD | 15/09/2022 | 30/10/2022 | DULAL MAJUMDER | 2.98 | 0 | 0 | 100
3 | HOWRAH | Bagnan - I | Howrah Division | Patinan Piped Water Supply Scheme | SM/13848 | New | Display Board at different PWSS at Bagnan-I Bagnan-II Block under uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000644/2023-2024 | 3219/AE/USD | 12/03/2024 | 11/04/2024 | ABONTICA ENTERPRISE | 4.76 | 2.38 | 50 | 100
4 | HOWRAH | Bagnan - I | Howrah Division | Patinan Piped Water Supply Scheme | SM/13848 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells at Patinan PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Part-B) | AE/Ulu | JE/USD | ORD/000724/2022-2023 | 513/HD | 09/02/2023 | 26/03/2023 | MENOKA ENGINEERING WORKS | 58.94 | 13.22 | 22.42 | 75
5 | HOWRAH | Bagnan - I | Howrah Division | Patinan Piped Water Supply Scheme | SM/13848 | New | Work Order for Sinking of 4 (Four) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Gopalpur PWSS 2nos & Patinan PWSS 2 Nos of Bagnan - I Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu |  | ORD/000745/2022-2023 | 663/HD | 17/02/2023 | 03/04/2023 | AQUATECH ENGINEER | 52.06 | 0 | 0 | 100
6 | HOWRAH | Bagnan - I | Howrah Division | Patinan Piped Water Supply Scheme | SM/13848 | New | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 1754/HD | 26/04/2023 |  | Resource Division | 22.05 | 0 | 0 | 0
7 | HOWRAH | Bagnan - I | Howrah Division | Patinan Piped Water Supply Scheme | SM/13848 | New | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 4695/HD | 26/12/2023 |  | Resource Division | 16.37 | 0 | 0 | 0
8 | HOWRAH | Bagnan - I | Electrical | Patinan Piped Water Supply Scheme | SM/13848 | New | Adhoc payment to WBSEDCL against service connnection |  |  | BILL/01127/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 109.23 | 0 | 0 | 0
9 | HOWRAH | Bagnan - I | Electrical | Patinan Piped Water Supply Scheme | SM/13848 | New | Quotation Bill for New Service Connection at Patinan W/S. Sch. |  |  | BILL/04030/2023-2024 | 316 | 03/10/2023 |  | WBSEDCL | 8.55 | 0 | 0 | 0
10 | HOWRAH | Bagnan - I | Electrical | Patinan Piped Water Supply Scheme | SM/13848 | New | Quotation Bill for New Service Connection at Patinan W/S. Sch. PH-II |  |  | BILL/04569/2023-2024 | 574 | 27/12/2023 |  | WBSEDCL | 4.2 | 0 | 0 | 0
11 | HOWRAH | Bagnan - I | Electrical | Patinan Piped Water Supply Scheme | SM/13848 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Patinan water supply scheme, T.W. No.- I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000163/2022-2023 | 3546/ED | 30/12/2022 | 30/03/2023 | M/S CHANDIMATA ELECTRICALS | 20.27 | 0 | 0 | 0
Total | [13 empty] | 516.78 | 103.98 | 20.12