## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Work Order for Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection) For Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P.H.E. Dte. From Node Section 255-287 to Node Section 90-91 From Node Section 287-304 to Node Section 448-450 (P-2,&4) | AE/SADAR | je_how_rws_jagat | ORD/000005/2023-2024 | 1532/HD | 04/04/2023 | 01/10/2023 | N. G ENGINEERING | 91.11 | 36.97 | 40.58 | 50
2 | HOWRAH |  | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Work Order for Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection-405 NOS) For Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P.H.E. Dte. From Node Section 456-457 to Node Section 522-530 Part 9 | AE/SADAR | je_how_rws_jagat | ORD/000006/2023-2024 | 1533/HD | 04/04/2023 | 01/10/2023 | JHARNA ENTERPRISE | 41.43 | 7 | 16.89 | 62
3 | HOWRAH |  | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Work Order for Construction of 700 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/8/2012) including Soil Investigation, Foundation Design & All pipe Connection, Laying Rising Main Pipeline Work, Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection)For Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah District under Howrah Division, P.H.E. Dte. From Node Section R1-1 to Node Section 280-281, Part 1 | AE/SADAR | je_how_rws_jagat | ORD/000027/2023-2024 | 1696/HD | 21/04/2023 | 15/02/2024 | PRAVAT SARKAR | 351.82 | 54.44 | 15.47 | 30
4 | HOWRAH |  | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Preparation of DPR for new piped water supply scheme of Deulpur PWSS, Panchla Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE/USD | ORD/000241/2022-2023 | 318/AE/USD | 16/08/2022 | 30/09/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.25 | 4.25 | 100 | 100
5 | HOWRAH |  | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Work Order for Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Deulpur Gangadharpur (Zone-II) PWSS of Panchla Block Howrah Sadar Sub-Division under Howrah Division, P. H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000660/2022-2023 | 172/HD | 13/01/2023 | 27/02/2023 | PRANTIK DRILLING AGENCY | 50.26 | 8.08 | 16.08 | 35
6 | HOWRAH |  | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Work Order for Laying Distribution System for Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. From Node Section 88-94 to Node Section 97-98 Part 3 | AE/SADAR | je_how_rws_jagat | ORD/000791/2022-2023 | 855/HD | 01/03/2023 | 31/03/2023 | DEBABRATA CHAKRABORTY | 16.89 | 7.08 | 41.91 | 58
7 | HOWRAH |  | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Work Order for Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. From Node Section 97-127 to Node Section 423-425 Part 5 | AE/SADAR | je_how_rws_jagat | ORD/000792/2022-2023 | 856/HD | 01/03/2023 | 31/03/2023 | S.S ENTERPRISE | 23.46 | 4 | 17.06 | 42
8 | HOWRAH |  | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Work Order for Laying Distribution System for Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Node Section 217-230 to Node Section 352-361 Part 7 | AE/SADAR | je_how_rws_jagat | ORD/000793/2022-2023 | 857/HD | 01/03/2023 | 15/04/2023 | DULAL MAJUMDER | 67.69 | 24.29 | 35.88 | 55
9 | HOWRAH |  | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Work Order for Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection) for Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Node Section 352- 405 to Node Section 532-534 Part 8 | AE/SADAR | je_how_rws_jagat | ORD/000794/2022-2023 | 875/H.D | 02/03/2023 | 30/06/2023 | M/S MSS RISING ENTERPRISE | 74.39 | 9.84 | 13.22 | 30
10 | HOWRAH |  | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Work Order for Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection) for Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Node Section 130-152 to Node Section 201-217 Part 6 | AE/SADAR | je_how_rws_jagat | ORD/000795/2022-2023 | 876/HD | 02/03/2023 | 30/06/2023 | K.B ENTERPRISE | 69.39 | 27.48 | 39.6 | 80
11 | HOWRAH |  | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Continuation order for Preparation of DPR with Route Survey for new piped water supply scheme of Deulpur Gangadharpur Zone-II PWSS of Panchla Block under Howrah Division PHE Dte. | AE/SADAR |  | ORD/000980/2022-2023 | 1507/HD | 21/07/2022 | 20/08/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.13 | 3.13 | 99.97 | 100
12 | HOWRAH |  | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000066/2022-2023 | 2839/HD | 23/12/2022 |  | Resource Division | 33.91 | 0 | 0 | 0
13 | HOWRAH |  | Howrah Division | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000087/2022-2023 | 446/HD | 06/02/2023 |  | Resource Division | 307.95 | 0 | 0 | 0
14 | HOWRAH |  | Electrical | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Quotation for new service connection charge at Gangadharpur Deulpur PWSS, Zone-II, TW - I |  |  | BILL/04487/2023-2024 | 529 | 15/12/2023 |  | WBSEDCL | 0.32 | 0 | 0 | 0
15 | HOWRAH |  | Electrical | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Deulpur & Gangadharpur water supply scheme, Zone-I, T.W. No. III and Zone-II, T.W. No. III Block: Panchla, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000875/2023-2024 | 3448/ED | 11/08/2023 | 09/11/2023 | R.M.D TRADING. | 21.99 | 0 | 0 | 0
16 | HOWRAH |  | Electrical | DEULPUR-GANGADHARPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/14154 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Deulpur & Gangadharpur water supply scheme, Zone-I, T.W. No. I & II and Zone-II, T.W. No. I & II Block: Panchla, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000921/2023-2024 | 3592/ED | 28/08/2023 | 26/11/2023 | R.N.S. TRADING | 43.65 | 0 | 0 | 0
Total | [13 empty] | 1201.64 | 186.55 | 15.52