## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Amta - I | Howrah Division | Sherpur Piped Water Supply Scheme | SM/18426 | New | Sinking of 05 (Five) nos Big dia Tube wells, Construction of Switch rooms(5.4x3.6) for HW site and other TW sites, Boundary walls, Land Developments, Laying distribution system (UPVC & HDPE & DI) & Providing Functional Household Tap Connection (FHTC), Interconnection between tubewells and OHR and Construction of OHR of 700 cum and 400 cum capacity 20.0 m staging height along with pipe connection etc for SHERPUR PWSS in Amta-I Block and Augmentation of JOARGARH PWSS in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC=8807] | AE/Ulu | JE-USD,JE/USD | ORD/000239/2023-2024 | 3488/HD | 29/09/2023 | 25/07/2024 | S.P. CONSTRUCTION | 1926.07 | 176.37 | 9.16 | 38
2 | HOWRAH | Amta - I | Howrah Division | Sherpur Piped Water Supply Scheme | SM/18426 | New | Material Requisition To Resource Division |  |  | RTOR000108/2023-2024 | 964/HD | 28/02/2024 |  | Resource Division | 65.52 | 0 | 0 | 0
3 | HOWRAH | Amta - I | Electrical | Sherpur Piped Water Supply Scheme | SM/18426 | New | Quotation for New Service Connection at Sherpur W/S. Sch. PH-I, Amta-I |  |  | BILL/04662/2023-2024 | 643 | 09/01/2024 |  | WBSEDCL | 3.9 | 0 | 0 | 0
4 | HOWRAH | Amta - I | Electrical | Sherpur Piped Water Supply Scheme | SM/18426 | New | Quotation for New Service Connection at Sherpur W/S. Sch. PH-II, Amta-I |  |  | BILL/04663/2023-2024 | 640 | 09/01/2024 |  | WBSEDCL | 4.17 | 0 | 0 | 0
5 | HOWRAH | Amta - I | Electrical | Sherpur Piped Water Supply Scheme | SM/18426 | New | Quotation for New Service Connection at Sherpur W/S. Sch. PH-III, Amta-I |  |  | BILL/04664/2023-2024 | 641 | 09/01/2024 |  | WBSEDCL | 6.98 | 0 | 0 | 0
6 | HOWRAH | Amta - I | Electrical | Sherpur Piped Water Supply Scheme | SM/18426 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sherpur water supply scheme, T.W. No. I, II & III, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/001888/2023-2024 | 63/ED | 08/01/2024 | 07/04/2024 | MAA KALI ENTERPRISE | 34.21 | 12.68 | 37.08 | 60
Total | [13 empty] | 2040.85 | 189.05 | 9.26