## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells, construction of 2 nos 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at TW Sites and 450 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including pile design for UDANG (ZONE-II) PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | AE/Ulu | JE/USD | ORD/000145/2023-2024 | 2839/HD | 07/08/2023 | 05/12/2023 | NATURAL RESOURCES CONSORTIUM | 501.82 | 25.35 | 5.05 | 0
2 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Laying Distribution System(HDPE & DI) & Providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells UDONG (ZONE-I) PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | AE/Ulu | JE/USD | ORD/000159/2023-2024 | 2977/HD | 17/08/2023 | 15/12/2023 | TAPU SAHA | 410.47 | 151.22 | 36.84 | 59
3 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Sinking of 3(Three) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Udang Zone-I & Zone-II 2 nos under Amta-I Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000191/2023-2024 | 3133/HD | 29/08/2023 | 13/10/2023 | NADIA TUBEWELLS | 38.94 | 12.34 | 31.67 | 68
4 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Work for Preparation of DPR for Augmentation of Udong PWSS, Amta-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE/USD | ORD/000219/2022-2023 | 314/AE/USD | 16/08/2022 | 30/09/2022 | MS SOBHA AND CO | 3.83 | 1.92 | 50 | 100
5 | HOWRAH |  | Electrical | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Quotation money deposition for new service connection at Udang w/s scheme, Zone- I, T.W. No.-IV, Dist.-Howrah under PHE Dte. Application No- 1007772514 Reference ID- 106595797 SM Code- 18567 |  |  | BILL/00492/2024-2025 | 165 | 28/05/2024 |  | WBSEDCL | 5.3 | 0 | 0 | null
6 | HOWRAH |  | Electrical | Augmentation of Ground Water Based Udang(Zone-I & II) Piped Water Supply Scheme | SM/18567 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Udang water supply scheme, T.W. No. I & II, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000923/2023-2024 | 3594/ED | 28/08/2023 | 26/11/2023 | EMCON | 21.49 | 0 | 0 | 0
Total | [13 empty] | 981.86 | 190.82 | 19.43