## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Amta - I | Howrah Division | Ground Water Based Raspur PWSS | SM/18719 | New | Sinking of big dia Tube wells, Construction of Switch rooms(5.4x3.6) for HW site and other TW sites, Boundary walls, Land Developments, Laying distribution system (HDPE & DI) & Providing House Hold Connection(FHTC), Interconnection between tube wells and OHR and Construction of OHR 350 cum capacity (DRG. NO.- PC-I/OHR/12/2012) 20.0mtr staging height along with pipe connection, soil investigation & design etc for Raspur PWSS in Amta-I Block under Uluberia Sub Division under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/BLK/amta1 | ORD/000223/2023-2024 | 3294/HD | 14/09/2023 | 10/07/2024 | GEE BEE NIRMAN CO PVT LTD | 831.69 | 0 | 0 | 20
2 | HOWRAH | Amta - I | Howrah Division | Ground Water Based Raspur PWSS | SM/18719 | New | Work Order for Preparation of DPR for new piped water supply scheme of Raspur PWSS, Amta-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE/BLK/amta1 | ORD/000438/2021-2022 | 239/HD | 07/02/2022 | 22/02/2022 | RADIANT | 3.87 | 0 | 0 | 100
3 | HOWRAH | Amta - I | Howrah Division | Ground Water Based Raspur PWSS | SM/18719 | New | Material Requisition To Resource Division |  |  | RTOR000033/2024-2025 | 4864/HD | 22/11/2024 | 22/11/2024 | Resource Division | 6.16 | 0 | 0 | 0
4 | HOWRAH | Amta - I | Howrah Division | Ground Water Based Raspur PWSS | SM/18719 | New | Material Requisition To Resource Division |  |  | RTOR000107/2023-2024 | 964/HD | 28/02/2024 | 28/02/2024 | Resource Division | 75.31 | 0 | 0 | 0
5 | HOWRAH | Amta - I | Electrical | Ground Water Based Raspur PWSS | SM/18719 | New | Quotation for Shifting of energy meter by drawl of new LT-AB cable line at Someswaer PHE(Roshpur PH-II) under Amta C.C.C Application No- 10000132287 Reference ID- 860328827 SM Code- 18719 |  |  | BILL/04014/2024-2025 |  | 13/03/2025 | 13/03/2025 | WBSEDCL | 0.85 | 0 | 0 | 0
6 | HOWRAH | Amta - I | Electrical | Ground Water Based Raspur PWSS | SM/18719 | New | Quotation for New Service Connection at Rashpur W/S. Sch. PH-I, Amta-I |  |  | BILL/04660/2023-2024 | 644 | 09/01/2024 | 09/01/2024 | WBSEDCL | 13.7 | 0 | 0 | 0
7 | HOWRAH | Amta - I | Electrical | Ground Water Based Raspur PWSS | SM/18719 | New | Quotation for New Service Connection at Rashpur W/S. Sch. PH-II, Amta-I |  |  | BILL/04661/2023-2024 | 642 | 09/01/2024 | 09/01/2024 | WBSEDCL | 11.6 | 0 | 0 | 0
8 | HOWRAH | Amta - I | Electrical | Ground Water Based Raspur PWSS | SM/18719 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Raspur water supply scheme, T.W. No.- I & II, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000939/2023-2024 | 3618/ED | 29/08/2023 | 20/05/2025 | SWAPAN ENTERPRISE | 20.37 | 0 | 0 | 80
Total | [13 empty] | 963.55 | 0 | 0