## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chandipur W/S Scheme including | SM/07398 | Retrofitting | Laying of UPVC pipe line for providing FHTC damaged due to upgradation of Road for Chandipur Water Supply Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001484/2021-2022 | 6394/AD | 02/03/2022 | 01/04/2022 | M/S RAKESH ENTERPRISE | 37.72 | 5.07 | 13.44 | 93
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 5 (five) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chandipur W/S Scheme including | SM/07398 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000833/2023-2024 | 678/AD | 30/01/2024 |  | Resource Division | 5.35 | 0 | 0 | 0
Total | [13 empty] | 43.08 | 5.07 | 11.77