## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including | SM/07576 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Uttar Durgapur and others of Hesamabad W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (PART-II) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000204/2020-2021 | 641/KSD | 19/08/2020 | 03/09/2020 | AVIRUP CONSTRUCTION | 4.48 | 6.22 | 138.92 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including | SM/07576 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Hesamabad and others of Hesamabad W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (PART-II) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000206/2020-2021 | 642/KSD | 19/08/2020 | 03/09/2020 | MAA LAXMI ENTERPRISE | 4.48 | 0 | 0 | 90
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including | SM/07576 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Dakshin Durgapur and others of Hesamabad W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (PART-III) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000208/2020-2021 | 643/KSD | 19/08/2020 | 03/09/2020 | M/S B. ENTERPRISE | 4.48 | 0 | 0 | 90
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including | SM/07576 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Booth No.- 184 and others of Hesamabad W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000447/2020-2021 | 833/KSD | 16/10/2020 | 30/11/2020 | MAA LAXMI ENTERPRISE | 3.26 | 0 | 0 | 90
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including | SM/07576 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Booth No. -180 of Hesamabad W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (Part-II) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000449/2020-2021 | 835/KSD | 16/10/2020 | 30/11/2020 | M/S B. ENTERPRISE | 4.51 | 8.91 | 197.81 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including | SM/07576 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Booth No.- 185 and others of Hesamabad W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000450/2020-2021 | 836/KSD | 16/10/2020 | 30/11/2020 | MAA LAXMI ENTERPRISE | 4.01 | 0 | 0 | 90
7 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including | SM/07576 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Booth No. -180 of Hesamabad W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (Part-I) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000455/2020-2021 | 843/KSD | 16/10/2020 | 30/11/2020 | M/S B. ENTERPRISE | 4.56 | 9.04 | 198.29 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including | SM/07576 | Retrofitting | Surging of 6 nos. Tubewell for Augmentation of Hesamabad- 2 nos., Block- Kakdwip, Herambagopalpur- 2 nos., Gurdaspur- 2 nos. W/S Scheme, Block - Pathar Pratima under JJM under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/000503/2024-2025 | 3606/AD | 06/09/2024 | 06/10/2024 | COPE ENTERPRISE | 8.23 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including | SM/07576 | Retrofitting | Surging and repairing of 2no Tube well of Hesamabad Water Supply Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/000596/2022-2023 | 5921/AD | 19/10/2022 | 03/11/2022 | S.K.GOLUI | 7.37 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including | SM/07576 | Retrofitting | Making and fixing of permanent display board at headwork site of Mrinalnagar, Koaberia, Hesamabad, Kakdwip, Kakdwip & Akshaynagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002144/2023-2024 | 944/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.94 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including | SM/07576 | Retrofitting | Repairing of 1 no. Pump House, boundary wall and approach road at 2nd Tubewell site for Hesamabad W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/07576) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002159/2024-2025 | 1989/KSD | 23/12/2024 | 17/01/2025 | IMAGINEER VENTURES | 2.06 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including | SM/07576 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Hesamabad and others of Hesamabad W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (PART-I) | Assistant Engineer, Kakdwip Sub Division |  | ORD/002501/2020-2021 | 611/KSD | 12/08/2020 | 27/08/2020 | MAA LAXMI ENTERPRISE | 4.47 | 0 | 0 | 90
13 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including | SM/07576 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Hesamabad and others of Hesamabad W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (PART-III) | Assistant Engineer, Kakdwip Sub Division |  | ORD/002502/2020-2021 | 627/KSD | 13/08/2020 | 28/08/2020 | MAA LAXMI ENTERPRISE | 4.48 | 0 | 0 | 90
14 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including | SM/07576 | Retrofitting | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Hesamabad PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (SM/07576) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/003193/2023-2024 | 1248/KSD | 27/12/2023 | 06/01/2024 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including | SM/07576 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000280/2023-2024 | 3079/AD | 28/09/2023 | 28/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including | SM/07576 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000839/2023-2024 | 684/AD | 30/01/2024 | 30/01/2024 | Resource Division | 6.8 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 6 (six) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hesamabad W/S Scheme including | SM/07576 | Retrofitting | Preparation of DPR including estimate for Providing FHTC at Hesamabad W/S Scheme (Phase-A), Chandipur W/S Scheme (Phase-A), Gangadharpur W/S Scheme (Phase-A) & Nebutala W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. [W/O No. 512/AD, 24.08.21, T.No. 1761/AD, 21-22] |  |  | VCH/002606/2021-2022 | BP-2021-22-509 | 22/03/2022 | 22/03/2022 | INDRANIL DUTTA & ASSOCIATES | 4.71 | 0 | 0 | 0
Total | [13 empty] | 69.63 | 24.17 | 34.72