## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 7 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar W/S Scheme including | SM/07590 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Srinagar Water Supply Scheme, Block - Kakdwip South 24 Pgs. District under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000497/2020-2021 | 5312/AD | 18/02/2021 | 18/02/2022 | MONDAL PRECISION PRIVATE LIMITED | 105.31 | 30.41 | 28.88 | 90
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 7 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar W/S Scheme including | SM/07590 | Retrofitting | Laying of UPVC pipe line for providing FHTC damaged due to upgradation of Road for Srinagar Water Supply Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001551/2021-2022 | 6727/AD | 17/03/2022 | 01/04/2022 | SUDIP PRADHAN | 11.34 | 0 | 0 | 90
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 7 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Srinagar W/S Scheme including | SM/07590 | Retrofitting | Laying D.I. Pipe Line for Rising Main and inter connection in between Tubewell No. 1 & Tubewell No. 2 for Srinagar W/S Scheme under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001935/2020-2021 | 1348/KSD | 23/02/2021 | 05/03/2021 | SARADA CONSTRUCTION | 4.77 | 0 | 0 | 80
Total | [13 empty] | 121.42 | 30.41 | 25.05