## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 02 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ananda Abad Water Supply S | SM/07593 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households at Ananda Abad Water Supply Scheme (Habitation- Ananda Abad), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division |  | ORD/000079/2022-2023 | 275/CSD | 19/05/2022 | 28/06/2022 | M/S. MANABESH ROY | 4.81 | 0 | 0 | 100
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 02 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ananda Abad Water Supply S | SM/07593 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Ananda Abad Water Supply Scheme Block - Basanti, South 24 Parganas District under Canning Sub Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of Scheme for 01 (one) year | Assistant Engineer, Canning sub division |  | ORD/001379/2020-2021 | 5370/AD | 19/02/2021 | 19/02/2022 | M/S. MANABESH ROY | 61.07 | 46.24 | 75.72 | 100
Total | [13 empty] | 65.88 | 46.24 | 70.19