## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kalaria Water Supply Schem | SM/07631 | Retrofitting | Laying of Distribution System of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IA), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (TSM/017465) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000527/2023-2024 | 2142/AD | 09/08/2023 | 07/11/2023 | PUTUL RANI MAITY | 217.06 | 0 | 0 | 60
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kalaria Water Supply Schem | SM/07631 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Kalaria Water Supply Scheme Block - Canning - I, South 24 Parganas District under Canning Sub Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of Scheme for 01 (one) year | Assistant Engineer, Canning sub division |  | ORD/001378/2020-2021 | 5132/AD | 08/02/2021 | 08/02/2022 | EFFLUENT & WATER TREATMENT ENGINEERS | 153.65 | 57.52 | 37.44 | 100
3 | SOUTH 24 PARAGANAS |  | Central Drilling | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kalaria Water Supply Schem | SM/07631 | Retrofitting | SALINE ZONE SEALING AND OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL IN KALARIA W/S SCHEME (REPLACEMENT TW-III, Z-II), UNDER SOUTH 24 PGS DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000508/2022-2023 | 309/CMSD-I | 08/07/2022 | 11/07/2022 | PADMA ENGINEERING & CO. | 0.58 | 0.29 | 49.12 | 100
4 | SOUTH 24 PARAGANAS |  | Central Drilling | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kalaria Water Supply Schem | SM/07631 | Retrofitting | Additional Mobilization of all machineries & accessories etc. and Sealing of Saline zone at site for construction of tube well at Kalaria W/S Scheme (untreated zone), South 24 pgs District. under, Central Drilling Division, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000522/2022-2023 | 257/CMSD-I(D) | 23/06/2022 | 26/06/2022 | PADMA ENGINEERING & CO. | 0.86 | 0.43 | 50 | 100
Total | [13 empty] | 372.15 | 58.24 | 15.65