## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07751 | Retrofitting | Extension of pipeline in connection with Functional Household Tap Connection (FHTC) at Ghoradal Uttar (Dakshinpara) and Fhatki Paschimpara under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000039/2022-2023 | 08/RSD | 04/04/2022 | 03/06/2022 | M/S R.K.ENTERPRISE | 4.77 | 4.77 | 100 | 100
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07751 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghoradal at Habitation - Gabbati (Part-B) in Ghoradal Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000270/2021-2022 | 380/RSD | 13/08/2021 | 12/10/2021 | M/S R.K.ENTERPRISE | 4.82 | 4.57 | 94.71 | 100
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07751 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households at Killa Dakshin (Part-1) in Ghoradal Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division |  | ORD/000291/2020-2021 | 376/RSD | 15/10/2020 | 14/11/2020 | L.N. ENTERPRISE | 4.76 | 4.76 | 100 | 0
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07751 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households at Killa Uttar (Part-1) in Ghoradal Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division |  | ORD/000292/2020-2021 | 377/RSD | 15/10/2020 | 14/11/2020 | L.N. ENTERPRISE | 4.76 | 4.76 | 100 | 0
5 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07751 | Retrofitting | Laying distribution system and other allied works for piped water supply at Zone - XI of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/07751 and SM/15466) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000532/2024-2025 | 3638/AD | 09/09/2024 | 24/10/2024 | SUJATA CONSTRUCTION | 26.06 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07751 | Retrofitting | Extension of Pipeline in connection with Functional Household Tap Connection (FHTC) from SI of schools to Dhopapara (node no. 167-172-176) at Ghoradal mouza under Ghoradal Water supply Scheme of Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001156/2021-2022 | 570/RSD | 15/12/2021 | 13/02/2022 | M/S R.K.ENTERPRISE | 4.68 | 4.68 | 100 | 100
7 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07751 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Mouza-Ghoradal at Habitation-Gabbati in Ghoradal piped water supply scheme , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001183/2021-2022 | 536/RSD | 30/11/2021 | 29/01/2022 | M/S. JHARNA ENTERPRISE | 4.76 | 4.7 | 98.72 | 100
8 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07751 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Mouza- Istaranpur at Habitation-Gabbati in Ghoradal piped water supply scheme , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001184/2021-2022 | 537/RSD | 30/11/2021 | 29/01/2022 | M/S R.K.ENTERPRISE | 4.8 | 4.14 | 86.38 | 100
9 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07751 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghoradal at Habitation - Gabbati (Part-A) in Ghoradal Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001214/2020-2021 | 561/RSD | 30/12/2020 | 28/02/2021 | L.N. ENTERPRISE | 4.82 | 4.55 | 94.36 | 0
10 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07751 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghoradal at Habitation - Ghoradal (Part-2) in Ghoradal Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001228/2020-2021 | 563/RSD | 30/12/2020 | 28/02/2021 | L.N. ENTERPRISE | 4.82 | 4.54 | 94.14 | 0
11 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07751 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghoradal at Habitation - Killa Dakshin (Part-2) in Ghoradal Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001231/2020-2021 | 565/RSD | 30/12/2020 | 28/02/2021 | M/S R.K.ENTERPRISE | 4.82 | 4.55 | 94.49 | 0
12 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07751 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghoradal at Habitation - Killa Uttar (Part-2) in Ghoradal Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001235/2020-2021 | 567/RSD | 30/12/2020 | 28/02/2021 | M/S R.K.ENTERPRISE | 4.82 | 4.54 | 94.18 | 0
13 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07751 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Mouza-Istaranpur at Habitation-Ulubati Istaranpur in Ghoradal piped water supply scheme, District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001485/2021-2022 | 710/RSD | 02/03/2022 | 01/05/2022 | L.N. ENTERPRISE | 4.22 | 4.17 | 98.75 | 100
14 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07751 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Mouza-Istaranpur at Habitation-Ulubati Istaranpur in Ghoradal piped water supply scheme, District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001545/2021-2022 | 710/RSD | 02/03/2022 | 01/05/2022 | L.N. ENTERPRISE | 4.22 | 0 | 0 | 100
15 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-XI, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/07751 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000633/2023-2024 | 237/AD | 15/01/2024 |  | Resource Division | 11.25 | 0 | 0 | 0
Total | [13 empty] | 98.38 | 54.72 | 55.62