## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Khasramkarerchhar W/S Scheme i | SM/07756 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Dakshin Para (Part) of Khasramkarchar W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000406/2020-2021 | 777/KSD | 14/10/2020 | 28/11/2020 | M/S. M.S. ENTERPRISE | 4.78 | 4.44 | 92.85 | 0
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Khasramkarerchhar W/S Scheme i | SM/07756 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Khasramkarchar (Part) of Khasramkarchar W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000418/2020-2021 | 795/KSD | 15/10/2020 | 29/11/2020 | M/S BABUSONA ENTERPRISE | 4.79 | 4.46 | 93.28 | 0
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Khasramkarerchhar W/S Scheme i | SM/07756 | Retrofitting | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Khas Ramkarchar (Phase-B) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000418/2023-2024 | 1907/AD | 01/08/2023 | 31/08/2023 | FORTUNE ENGINEERING | 25.22 | 11.19 | 44.38 | 100
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Khasramkarerchhar W/S Scheme i | SM/07756 | Retrofitting | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Muslim Para (Part) of Khasramkarchar W/S Scheme, Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000437/2020-2021 | 823/KSD | 16/10/2020 | 30/11/2020 | M/S. PAPIYA ENTERPRISE | 3.93 | 3.56 | 90.46 | 0
5 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Khasramkarerchhar W/S Scheme i | SM/07756 | Retrofitting | Surging of 2 nos. Tubewell for augmentation of Khas Ramkarchar W/S Scheme under JJM, Block - Sagar under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000526/2023-2024 | 352/KSD | 09/08/2023 | 29/08/2023 | S.K.GOLUI | 3.55 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Khasramkarerchhar W/S Scheme i | SM/07756 | Retrofitting | Construction of 300 cum. Capacity 20mtr. staging height RCC Over Head Reservoir at as per departmental design, drawing & specification etc.at Khas Ramkarer char W/s Scheme in 24 pgs (south) under Kakdwip Sub Division of Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001896/2018-2019 | 4984/AD | 04/03/2019 | 02/03/2025 | M/S. S.S. ENTERPRISE | 96.99 | 14.5 | 14.95 | 80
7 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Khasramkarerchhar W/S Scheme i | SM/07756 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000334/2023-2024 | 3149/AD | 29/09/2023 |  | Resource Division | 0.3 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Khasramkarerchhar W/S Scheme i | SM/07756 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000713/2023-2024 | 483/AD | 24/01/2024 |  | Resource Division | 8.91 | 0 | 0 | 0
Total | [13 empty] | 148.47 | 38.15 | 25.7