## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Radhakrishnapur W/S Scheme inc | SM/07759 | Retrofitting | Laying 63 mm dia. (OD) UPVC Pipe Line to cover house holds situated at Bahirplot far away from habitations of Radhakrishnapur W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000144/2021-2022 | 399/KSD | 07/07/2021 | 01/08/2021 | M/S. P. GIRI ENTERPRISE | 4.77 | 4.77 | 99.96 | 100
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Radhakrishnapur W/S Scheme inc | SM/07759 | Retrofitting | Laying 25 mm dia. & 15 mm dia. PVC Pipe Line to cover house holds situated at Radhakrishnapur and Bahirplot area which are far away from habitations of Radhakrishnapur W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000146/2021-2022 | 401/KSD | 07/07/2021 | 22/07/2021 | M/S. P. GIRI ENTERPRISE | 4.77 | 4.76 | 99.71 | 100
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Radhakrishnapur W/S Scheme inc | SM/07759 | Retrofitting | Laying 90 mm dia. (OD) UPVC Pipe Line to cover house holds situated far away from habitations of Radhakrishnapur W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000151/2021-2022 | 403/KSD | 07/07/2021 | 01/08/2021 | M/S. P. GIRI ENTERPRISE | 4.78 | 4.77 | 99.92 | 100
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Radhakrishnapur W/S Scheme inc | SM/07759 | Retrofitting | Laying 63 mm dia. (OD) UPVC Pipe Line to cover house holds situated at Radhakrishnapur far away from habitations of Radhakrishnapur W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000154/2021-2022 | 407/KSD | 07/07/2021 | 01/08/2021 | M/S. P. GIRI ENTERPRISE | 4.79 | 4.36 | 91.09 | 100
5 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Radhakrishnapur W/S Scheme inc | SM/07759 | Retrofitting | Laying Rising Main and inter connection of Tubewell and Supply and delivery of DI / CI specials for the same works for implementation of JJM of Radhakrishnapur Water Supply Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000353/2022-2023 | 338/KSD | 01/08/2022 | 21/08/2022 | M/S BABUSONA ENTERPRISE | 2.47 | 2.32 | 93.95 | 100
6 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Radhakrishnapur W/S Scheme inc | SM/07759 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Radhakrishnapur Water Supply Scheme, Block - Sagar, South 24 Parganas District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer,HQ-I |  | ORD/001277/2020-2021 | 2003/AD | 26/09/2020 | 26/09/2021 | M/S. P. GIRI ENTERPRISE | 59.38 | 51.34 | 86.47 | 100
7 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 4 (four) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Radhakrishnapur W/S Scheme inc | SM/07759 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000711/2023-2024 | 481/AD | 24/01/2024 |  | Resource Division | 6.08 | 0 | 0 | 0
Total | [13 empty] | 87.04 | 72.33 | 83.1