## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 16 (sixteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Gurudaspur W/S Scheme incl | SM/07760 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Gurudaspur Water Supply Scheme, Block - Patharpratima South 24 Pgs. District under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000499/2020-2021 | 5125/AD | 08/02/2021 | 08/02/2022 | DHIRENDRA ENGINEERING & CONSTRUCTION | 92.45 | 40.37 | 43.66 | 44
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 16 (sixteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Gurudaspur W/S Scheme incl | SM/07760 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000772/2023-2024 | 606/AD | 29/01/2024 |  | Resource Division | 23.82 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 16 (sixteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Gurudaspur W/S Scheme incl | SM/07760 | Retrofitting | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Gurudaspur W/S Scheme & it's adjacent areas, Block - Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. [2340/AD, 21-22, T.No. 1603/AD, 21-22] |  |  | VCH/002610/2021-2022 | BP-2021-22-513 | 23/03/2022 |  | LEMNISCATE | 2.67 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 16 (sixteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Gurudaspur W/S Scheme incl | SM/07760 | Retrofitting | Route Survey for Providing FHTC at Gurudaspur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. [W/O NO. 548/KSD, 03.09.21, T.NO. 1783/AD, 21-22] |  |  | VCH/002611/2021-2022 | BP-2021-22-514 | 23/03/2022 |  | M/S R.DUTTA & CO. | 4.26 | 0 | 0 | 0
Total | [13 empty] | 123.2 | 40.37 | 32.77