## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone II Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | SM/08119 | Retrofitting | HIRING OF AN Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer, DIAMOND HARBOUR SUB-DIVISION under Alipore Division, PHE Dte. (From 01.11.23 to 30.04.2023) |  |  | BILL/03385/2023-2024 | BP-2023-24-954 | 25/01/2024 |  | GOPAL KUMAR JHA | 0.7 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone II Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | SM/08119 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-II including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division |  | ORD/000068/2021-2022 | 343/AD | 12/05/2021 | 12/05/2022 | B. MOOKHERJEE | 310.16 | 121.34 | 39.12 | 100
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone II Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | SM/08119 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-II including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division |  | ORD/000077/2020-2021 | 5354/AD | 19/02/2021 | 19/02/2022 | B. MOOKHERJEE | 310.16 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone II Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | SM/08119 | Retrofitting | Relaying of distribution pipeline (damaged portion by open cut method) & road restoration near NP 92 & NP 77 at Zone-II of Falta Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000833/2022-2023 | 213/DHSD | 02/08/2022 | 16/09/2022 | B. MOOKHERJEE | 3.61 | 3.56 | 98.71 | 0
5 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone II Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | SM/08119 | Retrofitting | Relaying of distribution pipeline (damaged portion due to widening of road) in between NP 2 to NP 377 at Zone-II of Falta Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000834/2022-2023 | 214/DHSD | 02/08/2022 | 16/09/2022 | PEECON | 3.26 | 3.22 | 98.79 | 0
6 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone II Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | SM/08119 | Retrofitting | Laying of parallel distribution pipeline along opposite flank of Falta main road at Zone-II of Falta Block for "Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001652/2021-2022 | 454/DHSD | 15/03/2022 | 30/03/2022 | B. MOOKHERJEE | 4.8 | 4.8 | 99.94 | 100
7 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone II Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | SM/08119 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000100/2022-2023 | 7494/AD | 26/11/2022 |  | Resource Division | 2.69 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone II Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | SM/08119 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000431/2023-2024 | 3626/AD | 30/10/2023 |  | Resource Division | 6.16 | 0 | 0 | 0
9 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone II Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | SM/08119 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000846/2023-2024 | 784/AD | 03/02/2024 |  | Resource Division | 2.03 | 0 | 0 | 0
Total | [13 empty] | 643.55 | 132.91 | 20.65