## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone III Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Math | SM/08120 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-III including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division |  | ORD/000078/2020-2021 | 5443/AD | 24/02/2021 | 24/02/2022 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 341.46 | 238.83 | 69.94 | 90
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone III Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Math | SM/08120 | Retrofitting | Laying of distribution pipeline for balance portion providing remaining FHTC with allied works at Zone-III of Falta Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000373/2022-2023 | 4345/AD | 25/08/2022 | 24/09/2022 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 38.85 | 34.99 | 90.07 | 50
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone III Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Math | SM/08120 | Retrofitting | Re-laying of distribution pipeline (damaged portion) near Dighirpar Bazar area (in between NP 2-3,NP 5-86,NP 3-186 of Falta (Zone-III) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000826/2022-2023 | 210/DHSD | 02/08/2022 | 16/09/2022 | SRIJON ENTERPRISE | 4.56 | 4.35 | 95.32 | 0
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone III Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Math | SM/08120 | Retrofitting | Inter connection between secondary grid and inlet of OHR and restoration of compound area at OHR site of Falta Zone-III for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000828/2022-2023 | 211/DHSD | 02/08/2022 | 16/09/2022 | SRIJON ENTERPRISE | 2.82 | 2.66 | 94.34 | 0
5 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone III Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Math | SM/08120 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000021/2022-2023 | 1198/AD | 30/05/2022 |  | Resource Division | 3.98 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone III Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Math | SM/08120 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000848/2023-2024 | 786/AD | 03/02/2024 |  | Resource Division | 10.26 | 0 | 0 | 0
Total | [13 empty] | 401.94 | 280.83 | 69.87