## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone VI Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | SM/08121 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-VI including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division |  | ORD/000065/2021-2022 | 342/AD | 12/05/2021 | 12/05/2022 | BALAJEE ENTERPRISE. | 337.44 | 111.93 | 33.17 | 100
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone VI Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | SM/08121 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-I including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division |  | ORD/000076/2020-2021 | 5353/AD | 19/02/2021 | 19/02/2022 | M/S. S.S. ENTERPRISE | 440.86 | 51.34 | 11.64 | 100
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone VI Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | SM/08121 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-VI including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division |  | ORD/000080/2020-2021 | 5357/AD | 19/02/2021 | 19/02/2022 | BALAJEE ENTERPRISE. | 337.44 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone VI Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | SM/08121 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in Baidyakhali, Abad Simulgaunge, Pakurtala, Ahamedpur Mouza of Falta Zone-VI under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas Block Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000529/2022-2023 | 5514/AD | 29/09/2022 | 29/10/2022 | TIYASHA ENTERPRISE | 31.57 | 16.34 | 51.77 | 50
5 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone VI Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | SM/08121 | Retrofitting | Laying distribution system in left out portion for 100% coverage of Functional Household Tap Connection (FHTC) at Asta, Chaka,Guthari,Mahadebpur & Padmapur villages due to Swajal Gram activities under Zone-VI of Falta block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000579/2022-2023 | 5855/AD | 18/10/2022 | 02/11/2022 | BALAJEE ENTERPRISE. | 7.2 | 6.83 | 94.85 | 100
6 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone VI Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | SM/08121 | Retrofitting | Laying of distribution pipeline (leftout portion) over Kantakhali Lock gate and restoration of village concrete road damaged during FHTC work at Zone-VI of Falta Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000664/2022-2023 | 6169/AD | 01/11/2022 | 11/11/2022 | BALAJEE ENTERPRISE. | 3.98 | 3.96 | 99.65 | 100
7 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone VI Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | SM/08121 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000029/2021-2022 | 4346/AD | 04/03/2022 |  | Resource Division | 38.31 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution system of Zone VI Falta Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission & Jal Swapna under Mega Surface Water Based Water Supply Scheme for Falta-Mathu | SM/08121 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000433/2023-2024 | 3616/AD | 30/10/2023 |  | Resource Division | 14.78 | 0 | 0 | 0
Total | [13 empty] | 1211.59 | 190.4 | 15.71