## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dutta Babur Abad Water Supply Scheme including | SM/08635 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dutta Babur Abad Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000272/2021-2022 | 1719/AD | 17/08/2021 | 17/08/2022 | M/S. ROY CHOWDHURY & CO. | 120.85 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dutta Babur Abad Water Supply Scheme including | SM/08635 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000143/2023-2024 | 854/AD | 27/05/2023 |  | Resource Division | 1.72 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | Central Drilling | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dutta Babur Abad Water Supply Scheme including | SM/08635 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 300 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR DUTTABABUR ABAD W/S SCHEME (TW-II), CANNING-I BLOCK UNDER SOUTH 24PGS DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000064/2022-2023 | 55/CDD | 08/04/2022 | 08/05/2022 | C.M. ENTERPRISE | 14.55 | 13.54 | 93.06 | 0
4 | SOUTH 24 PARAGANAS |  | Central Drilling | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dutta Babur Abad Water Supply Scheme including | SM/08635 | Retrofitting | ADDITIONAL TRANSPORTATION OF GRAVELS, SEALING OF SALINE ZONE AND OTHERS AT SITE FOR CONSTRUCTION OF TUBE WELL IN DUTTA BABUR ABAD W/S SCHEME (TW-II), CANNING-I BLOCK UNDER SOUTH 24 PGS DISTRICT CDD, PHE DTE. |  |  | ORD/000221/2022-2023 | 418/CMSD-I | 10/08/2022 | 13/08/2022 | C.M. ENTERPRISE | 0.66 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | Central Drilling | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dutta Babur Abad Water Supply Scheme including | SM/08635 | Retrofitting | RESISTIVITY SURVEY OF TUBE WELLS AT SHIMULTALA W/S SCHEME, UNDER CMSD-I (D), CDD, PHE DTYE. |  |  | ORD/000235/2021-2022 | 109/CMSD-I (D) | 20/07/2021 | 27/07/2021 | EARTH CARE PRODUCTS & SERVICES | 0.52 | 0.26 | 50 | 0
6 | SOUTH 24 PARAGANAS |  | Central Drilling | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dutta Babur Abad Water Supply Scheme including | SM/08635 | Retrofitting | PROVIDING TUBEWELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AMODGHATA W/S SCH TW-II, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000366/2022-2023 | 378/CMSD-II | 01/08/2022 | 16/08/2022 | C.M. ENTERPRISE | 5 | 0 | 0 | 0
Total | [13 empty] | 143.3 | 13.8 | 9.63