## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bayarsing Water Supply Scheme including one year | SM/08637 | Retrofitting | LAUNCH HIRE CHARGES FOR OCT'22 TO DEC'22 UNDER CANNING SUB-DIVISION, PHE DTE. |  |  | BILL/00680/2024-2025 | BP-2024-25-224 | 20/06/2024 |  | RAJKUMAR MANNA | 1.1 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bayarsing Water Supply Scheme including one year | SM/08637 | Retrofitting | HIRE bill for month of JULY-SEP23 |  |  | BILL/03541/2023-2024 | BP-2023-24-1272 | 27/03/2024 |  | RAJKUMAR MANNA | 8.08 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bayarsing Water Supply Scheme including one year | SM/08637 | Retrofitting | Inter connection and rising main with supply of specials at PH-IV of Bayarsing Water Supply Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000198/2022-2023 | 2643/AD | 29/06/2022 | 29/07/2022 | SUDIP PRADHAN | 35.96 | 35.96 | 100 | 0
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bayarsing Water Supply Scheme including one year | SM/08637 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bayarsing Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000206/2021-2022 | 1423/AD | 27/07/2021 | 27/07/2022 | M/S. SAMADDAR CONSTRUCTION | 152.62 | 109.55 | 71.78 | 82
Total | [13 empty] | 197.77 | 145.52 | 73.58