## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Implementation of ISO/IEC 17025-2017 for NABL Accreditation for Bijoygarh District Water Testing Laboratory at Bijoygarh State General Hospital Campus under Alipur Division. | SM/08679 | Support-WQMSP | Construction of Civil Part for NABL accreditation of Bijoygarh District Water Testing Laboratory as per lSO/IEC 17025:2017 Related to Support Activities in the Dist. of South 24 Parganas under Alipore Division, P.H.E. Dte. | Assistant Engineer,HQ-I |  | ORD/000205/2021-2022 | 1422/AD | 27/07/2021 | 10/09/2021 | SUSHANTA MANDAL | 22.37 | 13.12 | 58.67 | 0
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Implementation of ISO/IEC 17025-2017 for NABL Accreditation for Bijoygarh District Water Testing Laboratory at Bijoygarh State General Hospital Campus under Alipur Division. | SM/08679 | Support-WQMSP | Supply of chemical, glassware and instruments requirement for NABL accreditation at South 24 Parganas District Water Testing Laboratory as per ISO/IEC: 17025: 2017 under Alipore Division, PHE Dte. in the district of South 24 Pgs. (2nd Call) | Assistant Engineer,HQ-I |  | ORD/000554/2021-2022 | 2618/AD | 28/09/2021 | 26/01/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 17.7 | 16.42 | 92.77 | 0
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Implementation of ISO/IEC 17025-2017 for NABL Accreditation for Bijoygarh District Water Testing Laboratory at Bijoygarh State General Hospital Campus under Alipur Division. | SM/08679 | Support-WQMSP | Remuneration of Chemist-Bacteriologist and Lab. Assistant of District Water Testing Laboratory, South 24 Parganas situated at Bijoygarh State General Hospital Complex, Kolkata under Alipore Division, PHE Dte. from 01/02/2022 to 31/01/2023. | Assistant Engineer,HQ-I |  | ORD/000938/2021-2022 | 4992/AD | 17/12/2021 | 17/12/2022 | NATURAL RESOURCES CONSORTIUM | 6.49 | 1.5 | 23.08 | 0
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Implementation of ISO/IEC 17025-2017 for NABL Accreditation for Bijoygarh District Water Testing Laboratory at Bijoygarh State General Hospital Campus under Alipur Division. | SM/08679 | Support-WQMSP | Engagement of 10(Ten) nos Lab. Personnal (Sampling Assistant and Lab. Attendent), actual travelling expenses and IEC activites to the Laboratory personnel for 07 nos Laboratories in the District. of South 24 Parganas under Alipore Division, PHE Dte.for the period from 01/01/2022 to 31/03/2022. | Assistant Engineer, RWS |  | ORD/001510/2021-2022 | 604/RWS | 30/12/2021 | 30/03/2022 | NATURAL RESOURCES CONSORTIUM | 3.75 | 2.84 | 75.73 | 0
Total | [13 empty] | 50.31 | 33.88 | 67.35