## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of ground water based Kanthalberia Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. | SM/08806 | Retrofitting | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for retrofitting of Kanthalberia W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000815/2022-2023 | 6810/AD | 16/11/2022 | 16/12/2022 | HARIDAS DUTTA | 19.49 | 0 | 0 | 95
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of ground water based Kanthalberia Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. | SM/08806 | Retrofitting | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site for Retrofitting of Kanthalberia W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000818/2022-2023 | 6813/AD | 16/11/2022 | 16/12/2022 | M/S BHUNIA ENTERPRISE | 7.18 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of ground water based Kanthalberia Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. | SM/08806 | Retrofitting | Survey work for Augmentation of ground water based Kanthalberia Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-I | Assistant Engineer, Canning sub division |  | ORD/001840/2021-2022 | 679CSD | 18/08/2021 | 02/09/2021 | HORIZEN | 1.99 | 1.84 | 92.49 | 100
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of ground water based Kanthalberia Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. | SM/08806 | Retrofitting | Design and DPR preparation for Augmentation of ground water based Kanthalberia Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-II | Assistant Engineer, Canning sub division |  | ORD/001841/2021-2022 | 680/CSD | 18/08/2021 | 02/09/2021 | HORIZEN | 3.19 | 3.19 | 100 | 100
5 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of ground water based Kanthalberia Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. | SM/08806 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000037/2021-2022 | 7033/AD | 31/03/2022 |  | Resource Division | 194.4 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of ground water based Kanthalberia Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. | SM/08806 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000391/2023-2024 | 332/AD | 19/01/2024 |  | Resource Division | 13.21 | 0 | 0 | 0
Total | [13 empty] | 239.45 | 5.03 | 2.1