## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Khan Saheber Abad Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08808 | Retrofitting | Preparation of DPR including estimate for Providing FHTC at Gangasagar W/S Scheme (Phase-A), Kachuberia W/S Scheme (Phase-A), Khansaheber Abad W/S Scheme (Phase-A) & Mandirlata W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001010/2021-2022 | 516/KSD | 24/08/2021 | 03/09/2021 | INDRANIL DUTTA & ASSOCIATES | 4.7 | 4.7 | 100 | 100
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Khan Saheber Abad Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08808 | Retrofitting | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Khansaheber Abad & Naraharipur W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001056/2021-2022 | 2344/AD | 09/09/2021 | 16/09/2021 | LEMNISCATE | 4.48 | 4.48 | 100 | 100
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Khan Saheber Abad Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08808 | Retrofitting | Route Survey for Providing FHTC at Khan Saheber Abad W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001082/2021-2022 | 573/KSD | 10/09/2021 | 30/09/2021 | M/S R.DUTTA & CO. | 3.88 | 3.17 | 81.73 | 100
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Khan Saheber Abad Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08808 | Retrofitting | Laying distribution system including Functional Household Tap Connection (FHTC) to all households for Augmentation of Khan Saheber Abad Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1000 ] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001085/2023-2024 | 3499/AD | 16/10/2023 | 14/01/2024 | S.P. CONSTRUCTION (V) | 110.29 | 0 | 0 | 50
5 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Khan Saheber Abad Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08808 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000321/2023-2024 | 3136/AD | 29/09/2023 |  | Resource Division | 0.3 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Khan Saheber Abad Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08808 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000536/2023-2024 | 20/AD | 02/01/2024 |  | Resource Division | 11.16 | 0 | 0 | 0
Total | [13 empty] | 134.8 | 12.35 | 9.16