## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Purusottampur Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08809 | Retrofitting | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Purusottampur W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001058/2021-2022 | 2346/AD | 09/09/2021 | 16/09/2021 | M/S R.DUTTA & CO. | 2.12 | 2.12 | 100 | 100
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Purusottampur Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08809 | Retrofitting | Route Survey for Providing FHTC at Purusottampur W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001085/2021-2022 | 576/KSD | 10/09/2021 | 30/09/2021 | ROY CHOWDHURY ASSOCIATES | 4.59 | 4.44 | 96.82 | 100
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Purusottampur Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08809 | Retrofitting | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Purusottampur Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001428/2023-2024 | 4611/AD | 14/12/2023 | 09/10/2024 | SPA ENTERPRISE | 641.07 | 0 | 0 | 35
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Purusottampur Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08809 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000322/2023-2024 | 3137/AD | 29/09/2023 |  | Resource Division | 0.3 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting for Providing FHTC at Ground Water Based Purusottampur Water Supply Scheme, Block : Sagar, District- South 24 Pgs. (Phase-A) | SM/08809 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000534/2023-2024 | 18/AD | 02/01/2024 |  | Resource Division | 12.38 | 0 | 0 | 0
Total | [13 empty] | 660.46 | 6.56 | 0.99