## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 19 (nineteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Devis Abad Water Supply Scheme including o | SM/09011 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 19 (nineteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Devis Abad Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000644/2021-2022 | 3697/AD | 22/11/2021 | 22/11/2022 | SPA ENTERPRISE | 172.91 | 36.95 | 21.37 | 48
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 19 (nineteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Devis Abad Water Supply Scheme including o | SM/09011 | Retrofitting | Inter connection and rising main works of Retrofitting of Devis Abad W/S Scheme, Block- Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (SM/09011) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001024/2023-2024 | 3399/AD | 11/10/2023 | 25/11/2023 | SPA ENTERPRISE | 26.17 | 8.01 | 30.61 | 75
Total | [13 empty] | 199.08 | 44.96 | 22.58