## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 05 (five) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramchandranagar Water Supply Scheme including | SM/09360 | Retrofitting | Surging and repairing of 1no Tube well of Ramchandranagar Water Supply Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/000599/2022-2023 | 5924/AD | 19/10/2022 | 03/11/2022 | S.K.GOLUI | 3.76 | 3.76 | 100 | 100
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 05 (five) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramchandranagar Water Supply Scheme including | SM/09360 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households at Ramchandranagar Water Supply scheme, Block - Kakdwip, South 24 Parganas District under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001144/2021-2022 | 5532/AD | 20/01/2022 | 20/01/2023 | M/S B.N.ENTERPRISE | 54.95 | 42.43 | 77.21 | 100
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 05 (five) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramchandranagar Water Supply Scheme including | SM/09360 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households at Suryanagar Water Supply scheme, Block - Kakdwip, South 24 Parganas District under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001567/2021-2022 | 6829/AD | 23/03/2022 | 07/05/2022 | M/S B. ENTERPRISE | 113.06 | 0 | 0 | 94
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 05 (five) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramchandranagar Water Supply Scheme including | SM/09360 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000017/2021-2022 | 5623/AD | 25/01/2022 |  | Resource Division | 4.51 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 05 (five) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Ramchandranagar Water Supply Scheme including | SM/09360 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000802/2023-2024 | 647/AD | 30/01/2024 |  | Resource Division | 2.54 | 0 | 0 | 0
Total | [13 empty] | 178.82 | 46.19 | 25.83