## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply at various MPCS & Schools (rescue centers) :- Fulbari Sitala High School and Bamankhali MPP High School at Sagar Block for preventive measurement of severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 25.05.2021 to 18.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000165/2021-2022 | 97/KSD | 22/05/2021 | 24/05/2021 | SUDIP PRADHAN | 1.98 | 1.98 | 100 | 0
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply at various MPCS & Schools (rescue centers) :- Muriganga F.P. School, Sumatinagar Sarat Kumari High School, Mrityunjoynagar F.P. School and Dhablat RKGM F.P. School at Sagar Block for preventive measurement of severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 25.05.2021 to 18.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000166/2021-2022 | 98/KSD | 22/05/2021 | 24/05/2021 | BIMALENDU GIRI | 4.03 | 4.03 | 100 | 0
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply at various MPCS & Schools (rescue centers) :- Prasadpur Atal Vidyabhaban, Dakshin Sagar Banitirtha High School and Gobindapur Tarachand High School at Sagar Block for preventive measurement of severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 25.05.2021 to 18.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000167/2021-2022 | 99/KSD | 22/05/2021 | 24/05/2021 | ANANTA KUMAR GIRI | 3.08 | 3.08 | 100 | 0
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply at various MPCS & Schools (rescue centers) :- Digambari F.P. School, Radhakrishnapur High School and Harinbari Yudhustir Adarsha Sikshaniketan at Sagar Block for preventive measurement of severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 25.05.2021 to 18.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000168/2021-2022 | 101/KSD | 22/05/2021 | 24/05/2021 | GROWING CONCERN | 3.06 | 3.06 | 100 | 0
5 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply arrangement through Submersible Pump at near Sitarampur 1no & 2no big dia tubewell (2 nos.) at G plot GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 27.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000172/2021-2022 | 105/KSD | 22/05/2021 | 24/05/2021 | M/S B. ENTERPRISE | 4.2 | 4.2 | 99.99 | 0
6 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply at various MPCS & Schools (rescue centers) :- Fatikpur Rishi Bankim SSK, Narayanpur 4th Ghari Pragati Sangha, Ganeshnagar Sarboday Gholapara FP School and Debnagar Paikbar FP School at Namkhana Block for preventive measurement of severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 25.05.2021 to 18.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000173/2021-2022 | 106/KSD | 22/05/2021 | 24/05/2021 | BIMALENDU GIRI | 4.01 | 4 | 99.94 | 0
7 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply at various MPCS & Schools (rescue centers) :- Dk. Chandanpiri FP School, Near Nabin FP School, Patibunia Nanigopal FP School and Rajganar Stinathgram Jr Basic School at Namkhana Block for preventive measurement of severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 25.05.2021 to 18.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000174/2021-2022 | 107/KSD | 22/05/2021 | 24/05/2021 | ANANTA KUMAR GIRI | 4.04 | 4.03 | 99.94 | 0
8 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply at various MPCS & Schools (rescue centers) :- Kusumtala Paschim Madhya Ghari FP School, Near Baliara FP School, Bijoybati Parvarta FP School and Near Debnibas Sub - Centre Field at Namkhana Block for preventive measurement of severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 25.05.2021 to 18.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000175/2021-2022 | 108/KSD | 22/05/2021 | 24/05/2021 | GROWING CONCERN | 4.02 | 4.01 | 99.72 | 0
9 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply at various MPCS & Schools (rescue centers) :- Ishwaripur Free Primary School, Mousuni First Portion Junior Basic School MPCS, Namkhana Narayan Vidyamandir MPCS, Haripur Gadadhar Vidyapith MPCS at Namkhana Block for preventive measurement of severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 25.05.2021 to 18.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000176/2021-2022 | 109/KSD | 22/05/2021 | 24/05/2021 | BIMALENDU GIRI | 4 | 4 | 99.96 | 0
10 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply at various MPCS & Schools (rescue centers) :- Vivekananda SSK, Bishalaxmipur Agarni Sangha, Siddhananda Balika Vidyalaya and Rajnagar Bani Vidyapith High School at Namkhana Block for preventive measurement of severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 25.05.2021 to 18.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000177/2021-2022 | 110/KSD | 22/05/2021 | 24/05/2021 | ANANTA KUMAR GIRI | 4.02 | 4.02 | 99.96 | 0
11 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply at various MPCS & Schools (rescue centers) :- Freserganj KPA High School, Debnibas Flood Centre, Bijaybati Flood Centre and Dhaneswar Shiksha Sadan at Namkhana Block for preventive measurement of severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 25.05.2021 to 18.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000178/2021-2022 | 111/KSD | 22/05/2021 | 24/05/2021 | GROWING CONCERN | 4.04 | 0 | 0 | 0
12 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply at various MPCS & Schools (rescue centers) :- Chandanpiri M.M. High School (H.S.), Uttar Chandanpiri Sriniketan SSK, Chandanpiri FP School and Dk. Chandanpiri Flood Centre at Namkhana Block for preventive measurement of severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 25.05.2021 to 18.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000179/2021-2022 | 112/KSD | 22/05/2021 | 24/05/2021 | ANANTA KUMAR GIRI | 4.02 | 4.02 | 99.96 | 0
13 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply at various MPCS & Schools (rescue centers) :- Baliara Flood Centre, Baliara Kishore High School, Baliara Abinash Smriti FP School and Baliara South Adibashi FP School at Namkhana Block for preventive measurement of severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 25.05.2021 to 18.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000180/2021-2022 | 113/KSD | 22/05/2021 | 24/05/2021 | GROWING CONCERN | 4.04 | 4.03 | 99.96 | 0
14 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply at various MPCS & Schools (rescue centers) :- Debnagar Paikbar Flood Centre, Dwariknagar High School, Khetramohan F.P. and Dk. Durgapur Chanchalamayee at Namkhana Block for preventive measurement of severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 25.05.2021 to 18.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000181/2021-2022 | 114/KSD | 22/05/2021 | 24/05/2021 | BIMALENDU GIRI | 4.03 | 4.02 | 99.94 | 0
15 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply at various MPCS & Schools (rescue centers) :- Narayanpur Lakshmi Narayan Vidyamandir, Namkhana Narayan Vidyamandir, Nandabhanga FP School and Dk. Durgapur F.P. at Namkhana Block for preventive measurement of severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 25.05.2021 to 18.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000182/2021-2022 | 115/KSD | 22/05/2021 | 24/05/2021 | ANANTA KUMAR GIRI | 3.99 | 3.99 | 99.94 | 0
16 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply arrangement through Submersible Pump at Tukra gopalnagar Khudiram SSK & Dityeo khando gopalnagar (2 nos.) at Gopalnagar GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000227/2021-2022 | 150/KSD | 25/05/2021 | 27/05/2021 | M/S B. ENTERPRISE | 4.12 | 4.11 | 99.92 | 0
17 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply arrangement through Submersible Pump at Lahiripara & Bhuniamore (2 nos.) at Gopalnagar GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000230/2021-2022 | 153/KSD | 25/05/2021 | 27/05/2021 | BIMALENDU GIRI | 4.11 | 4.11 | 99.93 | 0
18 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply arrangement through Submersible Pump at Tritiya Khando & Durbachati Hashinath Bera house (2 nos.) at Durbachati GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000231/2021-2022 | 154/KSD | 25/05/2021 | 27/05/2021 | GROWING CONCERN | 4.12 | 4.11 | 99.94 | 0
19 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply arrangement through Submersible Pump at Kamdebnagar Nibedita SSK & Rathtala more (2 nos.) at Durbachati GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000233/2021-2022 | 156/KSD | 25/05/2021 | 27/05/2021 | ANANTA KUMAR GIRI | 4.11 | 4.11 | 99.94 | 0
20 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply arrangement through Submersible Pump at Laya ghat Shakti Das house & Paschim Dawrakapur ferighat near Parimal Giri house (2 nos.) at Patharpratima GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000235/2021-2022 | 158/KSD | 25/05/2021 | 27/05/2021 | BIMALENDU GIRI | 4.11 | 4.11 | 99.94 | 0
21 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply arrangement through Submersible Pump at Paschim Dwarakapur Adibashi para & Borodapur ashram FP School near Aswini Jana house (2 nos.) at Patharpratima GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000236/2021-2022 | 159/KSD | 25/05/2021 | 27/05/2021 | M/S B. ENTERPRISE | 4.11 | 4.11 | 99.94 | 0
22 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply arrangement through Submersible Pump at Bairagipara near Chandi Maity house & Arjun more Gramin mandir (2 nos.) at Ramganga GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000237/2021-2022 | 160/KSD | 25/05/2021 | 27/05/2021 | M/S B. ENTERPRISE | 4.11 | 4.11 | 99.95 | 0
23 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply arrangement through Submersible Pump at Janapara Ration shop & Janapara Deshpran School (2 nos.) at Ramganga GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) |  | Juniour Engineer_5, Kakdwip Sub Division | ORD/000238/2021-2022 | 161/KSD | 25/05/2021 | 27/05/2021 | ANANTA KUMAR GIRI | 4.12 | 4.12 | 99.95 | 0
24 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply arrangement through Submersible Pump at Kayamuri Vivekananda SSK school & Purba Surendranagar Uttar pally (2 nos.) at Herambagopalpur GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000240/2021-2022 | 163/KSD | 25/05/2021 | 27/05/2021 | GROWING CONCERN | 4.11 | 4.11 | 99.93 | 0
25 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply arrangement through Submersible Pump at near Kumarpur ICDS centre & Purba Dawrakapur Bisalacmi Mandir (2 nos.) at Laxmijanardanpur GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000242/2021-2022 | 165/KSD | 25/05/2021 | 27/05/2021 | M/S RAKESH ENTERPRISE | 4.11 | 4.11 | 99.96 | 0
26 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply arrangement through Submersible Pump at near Kerokhali FP School, Digambarpur GP & Kayal bazar, Sridharnagar GP (2 nos.) affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000246/2021-2022 | 168/KSD | 25/05/2021 | 27/05/2021 | ANANTA KUMAR GIRI | 4.12 | 4.11 | 99.92 | 0
27 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | temporary water supply arrangement through Submersible Pump at near Ratan Giri house, Sridharnagar GP & Sabuj bazar Hosen Gayen house, G plot GP (2 nos.) affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000264/2021-2022 | 170/KSD | 25/05/2021 | 27/05/2021 | GROWING CONCERN | 4.11 | 4.11 | 99.94 | 0
28 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply arrangement through Submersible Pump at near Vivekananda High School & Buraburir tat bazar (2 nos.) at G plot GP affected by Severe Cyclone YASS at Patharpratima Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 28.05.21 to 26.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000266/2021-2022 | 172/KSD | 25/05/2021 | 27/05/2021 | M/S B. ENTERPRISE | 4.11 | 3.96 | 96.19 | 0
29 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply arrangement through Submersible Pump near at Bagdanga Mousuni F.P. School and Mousuni Jamia Sadar Masjid at Mousuni GP, Block - Namkhana affected by Severe Cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 27.05.21 to 25.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000267/2021-2022 | 173/KSD | 25/05/2021 | 27/05/2021 | FORTUNE ENGINEERING | 4.12 | 4.12 | 99.84 | 0
30 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Temporary water supply arrangement through Submersible Pump near at Baliara F.P. School and Baliara Nimna Buniadi Adibashi School at Mousuni GP, Block - Namkhana affected by Severe Cyclone YASS at Namkhana Block under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 27.05.21 to 25.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000268/2021-2022 | 174/KSD | 25/05/2021 | 27/05/2021 | SARADA CONSTRUCTION | 4.1 | 4.1 | 99.81 | 0
31 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Repairing of Cement Concrete Canal Lining, dewatering, washing and cleaning of mud from floor of different buildings within PHE Complex at Sagar after severe cyclone YASS under Kakdwip Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000283/2021-2022 | 329/KSD | 03/06/2021 | 23/06/2021 | SUDIP PRADHAN | 1.12 | 1.12 | 99.96 | 0
32 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Surging of 10 nos. existing tube well with chemical treatment and bucket washing at different location of G.P. - Mousuni, Blcok - Namkhana due to affected by severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000285/2021-2022 | 331/KSD | 03/06/2021 | 18/06/2021 | BIMALENDU GIRI | 2.41 | 2.41 | 100 | 0
33 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Surging of 14 nos. existing tube well with chemical treatment and bucket washing at different location of G.P. - Mousuni, Blcok - Namkhana due to affected by severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000287/2021-2022 | 333/KSD | 03/06/2021 | 18/06/2021 | DEBARATI ENTERPRISE | 3.37 | 3.37 | 100 | 0
34 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Surging of 15 nos. existing tube well with chemical treatment and bucket washing at different location of G.P. - Mousuni, Blcok - Namkhana due to affected by severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000288/2021-2022 | 334/KSD | 03/06/2021 | 18/06/2021 | SARADA CONSTRUCTION | 3.61 | 3.61 | 100 | 0
35 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Surging of 16 nos. existing tube well with chemical treatment and bucket washing at different location of G.P. - Mousuni, Blcok - Namkhana due to affected by severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000289/2021-2022 | 335/KSD | 03/06/2021 | 18/06/2021 | BIMALENDU GIRI | 3.86 | 3.86 | 100 | 0
36 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Surging of 17 nos. existing tube well with chemical treatment and bucket washing at different location of G.P. - Mousuni, Blcok - Namkhana due to affected by severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000290/2021-2022 | 336/KSD | 03/06/2021 | 18/06/2021 | ANANTA KUMAR GIRI | 4.09 | 4.09 | 100 | 0
37 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Surging of 18 nos. existing tube well with chemical treatment and bucket washing at different location of G.P. - Mousuni, Blcok - Namkhana due to affected by severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000291/2021-2022 | 337/KSD | 03/06/2021 | 18/06/2021 | FORTUNE ENGINEERING | 4.34 | 4.34 | 100 | 0
38 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Surging of 19 nos. existing tube well with chemical treatment and bucket washing at different location of G.P. - Mousuni, Blcok - Namkhana due to affected by severe cyclone YASS under Kakldwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000292/2021-2022 | 338/KSD | 03/06/2021 | 18/06/2021 | GROWING CONCERN | 4.58 | 4.58 | 100 | 0
39 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Taktipur, Nebutala, Chandipur W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Kakdwip Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 27.05.2021 to 31.05.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000293/2021-2022 | 122/KSD | 25/05/2021 | 30/05/2021 | SARADA CONSTRUCTION | 4.79 | 4.79 | 100 | 0
40 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Kashinagar, Kalinagar, Ganeshpur W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Kakdwip Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 27.05.2021 to 31.05.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000294/2021-2022 | 123/KSD | 25/05/2021 | 30/05/2021 | FORTUNE ENGINEERING | 4.77 | 4.75 | 99.58 | 0
41 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Suryanagar, Ramchandranagar, Shibkalinagar W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Kakdwip Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 27.05.2021 to 31.05.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000295/2021-2022 | 124/KSD | 25/05/2021 | 30/05/2021 | SARADA CONSTRUCTION | 4.74 | 4.71 | 99.46 | 0
42 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Gobindarampur & Gangadharpur W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Kakdwip Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 27.05.2021 to 31.05.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000296/2021-2022 | 125/KSD | 25/05/2021 | 30/05/2021 | PIKASU BOSE | 4.76 | 4.72 | 99.16 | 0
43 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Akshaynagar & Akhaynagar (Aug) W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Kakdwip Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 27.05.2021 to 31.05.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000297/2021-2022 | 126/KSD | 25/05/2021 | 30/05/2021 | M/S UJJAL ENTERPRISE | 4.79 | 4.75 | 99.17 | 0
44 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Kachuberia, Mandirtala & Krishnanagar W/S Scheme at Sagar Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Period from 27.05.2021 to 31.05.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000298/2021-2022 | 127/KSD | 25/05/2021 | 30/05/2021 | BIMALENDU GIRI | 4.81 | 4.81 | 100 | 0
45 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Companirchar, Khasramkarchar & Khansaheber Abad W/S Scheme at Sagar Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Period from 27.05.2021 to 31.05.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000299/2021-2022 | 128/KSD | 25/05/2021 | 30/05/2021 | GROWING CONCERN | 4.81 | 4.81 | 100 | 0
46 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Radhakrishnapur & Kamalpur Rudranagar W/S Scheme at Sagar Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Period from 27.05.2021 to 31.05.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000300/2021-2022 | 129/KSD | 25/05/2021 | 30/05/2021 | ANANTA KUMAR GIRI | 4.81 | 4.81 | 100 | 0
47 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Nagendraganj, Dhaspara & Haradhanpur W/S Scheme at Sagar Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Period from 27.05.2021 to 31.05.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000301/2021-2022 | 130/KSD | 25/05/2021 | 30/05/2021 | BIMALENDU GIRI | 4.81 | 4.81 | 100 | 0
48 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Mahishamari W/S Scheme at Sagar Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. 27.05.2021 to 31.05.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000302/2021-2022 | 131/KSD | 25/05/2021 | 30/05/2021 | M/S KHAJABABA ENTERPRISE | 4.08 | 4.08 | 100 | 0
49 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Chemaguri W/S Scheme at Sagar Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. 27.05.2021 to 31.05.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000303/2021-2022 | 132/KSD | 25/05/2021 | 30/05/2021 | M/S KHAJABABA ENTERPRISE | 4.1 | 4.1 | 100 | 0
50 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Gangasagar W/S Scheme at Sagar Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. 27.05.2021 to 31.05.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000304/2021-2022 | 133/KSD | 25/05/2021 | 30/05/2021 | M/S KHAJABABA ENTERPRISE | 4.1 | 4.1 | 100 | 0
51 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Haripur and Rajnagar W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Namkhana Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 27.05.2021 to 31.05.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000305/2021-2022 | 134/KSD | 25/05/2021 | 30/05/2021 | GROWING CONCERN | 4.82 | 4.8 | 99.59 | 0
52 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Debnibus and Shibpur W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Namkhana Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 27.05.2021 to 31.05.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000306/2021-2022 | 135/KSD | 25/05/2021 | 30/05/2021 | ANANTA KUMAR GIRI | 4.7 | 4.7 | 100 | 0
53 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Budhakhali (Zone - I & II) W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Namkhana Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 27.05.2021 to 31.05.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000307/2021-2022 | 136/KSD | 25/05/2021 | 30/05/2021 | BIMALENDU GIRI | 4.7 | 4.68 | 99.58 | 0
54 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Namkhana W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Namkhana Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 27.05.2021 to 31.05.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000308/2021-2022 | 137/KSD | 25/05/2021 | 30/05/2021 | ANANTA KUMAR GIRI | 4.84 | 4.82 | 99.59 | 0
55 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Narayanpur W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Namkhana Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 27.05.2021 to 31.05.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000309/2021-2022 | 138/KSD | 25/05/2021 | 30/05/2021 | GROWING CONCERN | 4.81 | 4.79 | 99.59 | 0
56 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Kusumtala W/S Scheme and other adjoining areas of G.P. - Mousuni affected due to severe cyclone YASS at Namkhana Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 27.05.2021 to 31.05.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000310/2021-2022 | 139/KSD | 25/05/2021 | 30/05/2021 | ANANTA KUMAR GIRI | 4.81 | 4.81 | 100 | 0
57 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Herambogopalpur W/S Scheme at Pathar Pratima Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 27.05.2021 to 31.05.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000311/2021-2022 | 140/KSD | 25/05/2021 | 30/05/2021 | M/S B. ENTERPRISE | 4.78 | 3.45 | 72.22 | 0
58 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Paschim Surendranagar Zone-I W/S Scheme at Pathar Pratima Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 27.05.2021 to 31.05.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000313/2021-2022 | 142/KSD | 25/05/2021 | 30/05/2021 | M/S B. ENTERPRISE | 4.77 | 4.77 | 100 | 0
59 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Sumatinagar & Purusottampur W/S Scheme at Sagar Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Period from 27.05.2021 to 31.05.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000326/2021-2022 | 146/KSD | 25/05/2021 | 30/05/2021 | ANANTA KUMAR GIRI | 4.81 | 4.81 | 100 | 0
60 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Taktipur, Nebutala, Chandipur W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Kakdwip Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 01.06.2021 to 07.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000327/2021-2022 | 186/KSD | 31/05/2021 | 07/06/2021 | SARADA CONSTRUCTION | 4.67 | 4.63 | 99.15 | 0
61 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Kashinagar, Kalinagar, Ganeshpur W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Kakdwip Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 01.06.2021 to 07.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000328/2021-2022 | 187/KSD | 31/05/2021 | 07/06/2021 | FORTUNE ENGINEERING | 4.71 | 4.69 | 99.58 | 0
62 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Suryanagar, Ramchandranagar, Shibkalinagar W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Kakdwip Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 01.06.2021 to 07.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000329/2021-2022 | 188/KSD | 31/05/2021 | 07/06/2021 | KRISHNA CONSTRUCTION | 4.7 | 4.65 | 99.03 | 0
63 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Gobindarampur & Gangadharpur W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Kakdwip Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 01.06.2021 to 07.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000330/2021-2022 | 189/KSD | 31/05/2021 | 07/06/2021 | M/S UJJAL ENTERPRISE | 4.76 | 4.72 | 99.16 | 0
64 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Akshaynagar & Akhaynagar (Aug) W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Kakdwip Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 01.06.2021 to 07.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000332/2021-2022 | 190/KSD | 31/05/2021 | 07/06/2021 | PIKASU BOSE | 4.82 | 4.77 | 98.95 | 0
65 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Ramratanpur and Ramtanunagar W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Kakdwip Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 01.06.2021 to 07.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000335/2021-2022 | 191/KSD | 31/05/2021 | 07/06/2021 | SARADA CONSTRUCTION | 1.92 | 1.92 | 100 | 0
66 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Kachuberia, Mandirtala & Krishnanagar W/S Scheme at Sagar Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Period from 01.06.2021 to 07.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000336/2021-2022 | 192/KSD | 31/05/2021 | 07/06/2021 | BIMALENDU GIRI | 4.83 | 4.83 | 100 | 0
67 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Companirchar, Khasramkarchar & Khansaheber Abad W/S Scheme at Sagar Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Period from 01.06.2021 to 07.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000338/2021-2022 | 193/KSD | 31/05/2021 | 07/06/2021 | ANANTA KUMAR GIRI | 4.83 | 4.83 | 100 | 0
68 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Radhakrishnapur & Kamalpur Rudranagar W/S Scheme at Sagar Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Period from 01.06.2021 to 07.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000339/2021-2022 | 194/KSD | 31/05/2021 | 07/06/2021 | GROWING CONCERN | 4.83 | 4.83 | 100 | 0
69 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Nagendraganj, Dhaspara & Haradhanpur W/S Scheme at Sagar Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Period from 01.06.2021 to 07.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000340/2021-2022 | 195/KSD | 31/05/2021 | 07/06/2021 | PIKASU BOSE | 3.81 | 3.81 | 100 | 0
70 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Haripur and Rajnagar W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Namkhana Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 01.06.2021 to 07.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000345/2021-2022 | 196/KSD | 31/05/2021 | 07/06/2021 | GROWING CONCERN | 4.79 | 4.77 | 99.59 | 0
71 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Debnibus and Shibpur W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Namkhana Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 01.06.2021 to 07.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000348/2021-2022 | 197/KSD | 31/05/2021 | 07/06/2021 | BIMALENDU GIRI | 4.74 | 4.72 | 99.58 | 0
72 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Budhakhali (Zone - I & II) W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Namkhana Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 01.06.2021 to 07.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000353/2021-2022 | 198/KSD | 31/05/2021 | 07/06/2021 | ANANTA KUMAR GIRI | 4.76 | 4.76 | 100 | 0
73 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Namkhana W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Namkhana Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from Peroid from 01.06.2021 to 07.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000364/2021-2022 | 199/KSD | 31/05/2021 | 07/06/2021 | GROWING CONCERN | 4.77 | 4.75 | 99.58 | 0
74 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Narayanpur W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Namkhana Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 01.06.2021 to 07.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000365/2021-2022 | 200/KSD | 31/05/2021 | 07/06/2021 | GROWING CONCERN | 4.69 | 4.67 | 99.58 | 0
75 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Kusumtala W/S Scheme and other adjoining areas of G.P. - Mousuni affected due to severe cyclone YASS at Namkhana Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 01.06.2021 to 07.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000366/2021-2022 | 201/KSD | 31/05/2021 | 07/06/2021 | FORTUNE ENGINEERING | 4.84 | 4.82 | 99.59 | 0
76 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Herambogopalpur W/S Scheme at Pathar Pratima Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 01.06.2021 to 07.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000368/2021-2022 | 202/KSD | 31/05/2021 | 07/06/2021 | M/S B. ENTERPRISE | 4.77 | 4.77 | 100 | 0
77 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Taktipur, Nebutala, Chandipur W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Kakdwip Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 08.06.2021 to 26.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000369/2021-2022 | 307/KSD | 02/06/2021 | 21/06/2021 | SARADA CONSTRUCTION | 4.68 | 4.66 | 99.46 | 0
78 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Kashinagar, Kalinagar, Ganeshpur W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Kakdwip Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 08.06.2021 to 26.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000370/2021-2022 | 308/KSD | 02/06/2021 | 21/06/2021 | FORTUNE ENGINEERING | 4.74 | 4.72 | 99.58 | 0
79 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Suryanagar, Ramchandranagar, Shibkalinagar W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Kakdwip Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 08.06.2021 to 26.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000371/2021-2022 | 309/KSD | 02/06/2021 | 21/06/2021 | M/S RAKESH ENTERPRISE | 4.72 | 4.67 | 98.92 | 0
80 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Gobindarampur & Gangadharpur W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Kakdwip Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 08.06.2021 to 26.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000372/2021-2022 | 310/KSD | 02/06/2021 | 21/06/2021 | GROWING CONCERN | 4.79 | 4.74 | 98.94 | 0
81 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Akshaynagar & Akhaynagar (Aug) W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Kakdwip Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 08.06.2021 to 26.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000373/2021-2022 | 311/KSD | 02/06/2021 | 21/06/2021 | M/S RAKESH ENTERPRISE | 4.72 | 4.72 | 100 | 0
82 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Sumatinagar & Purusottampur W/S Scheme at Sagar Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Period from 08.06.2021 to 28.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000374/2021-2022 | 312/KSD | 02/06/2021 | 23/06/2021 | BIMALENDU GIRI | 2.82 | 2.82 | 100 | 0
83 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Nagendraganj, Dhaspara & Haradhanpur W/S Scheme at Sagar Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Period from 08.06.2021 to 28.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000375/2021-2022 | 313/KSD | 02/06/2021 | 23/06/2021 | GROWING CONCERN | 2.54 | 2.54 | 100 | 0
84 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Radhakrishnapur & Kamalpur Rudranagar W/S Scheme at Sagar Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Period from 08.06.2021 to 28.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000376/2021-2022 | 314/KSD | 02/06/2021 | 23/06/2021 | ANANTA KUMAR GIRI | 2.54 | 2.54 | 100 | 0
85 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Haripur and Rajnagar W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Namkhana Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 08.06.2021 to 28.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000430/2021-2022 | 315/KSD | 02/06/2021 | 23/06/2021 | GROWING CONCERN | 4.77 | 4.77 | 100 | 0
86 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Debnibus and Shibpur W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Namkhana Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 08.06.2021 to 28.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000431/2021-2022 | 316/KSD | 02/06/2021 | 23/06/2021 | BIMALENDU GIRI | 4.76 | 4.74 | 99.58 | 0
87 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Budhakhali (Zone - I & II) W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Namkhana Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 08.06.2021 to 28.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000432/2021-2022 | 317/KSD | 02/06/2021 | 23/06/2021 | ANANTA KUMAR GIRI | 4.81 | 4.78 | 99.47 | 0
88 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Namkhana W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Namkhana Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from Peroid from 08.06.2021 to 28.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000433/2021-2022 | 318/KSD | 02/06/2021 | 23/06/2021 | GROWING CONCERN | 4.72 | 4.72 | 100 | 0
89 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Narayanpur W/S Scheme and other adjoining areas, affected due to severe cyclone YASS at Namkhana Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 08.06.2021 to 28.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000434/2021-2022 | 319/KSD | 02/06/2021 | 23/06/2021 | BIMALENDU GIRI | 4.85 | 4.83 | 99.48 | 0
90 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Kusumtala W/S Scheme and other adjoining areas of G.P. - Mousuni affected due to severe cyclone YASS at Namkhana Block under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid from 08.06.2021 to 28.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000435/2021-2022 | 320/KSD | 02/06/2021 | 23/06/2021 | DEBARATI ENTERPRISE | 4.74 | 4.74 | 100 | 0
91 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Paschim Surendranagar Zone-I W/S Scheme at Pathar Pratima Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Peroid : 08.06.21 to 28.06.21) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000438/2021-2022 | 323/ksd | 02/06/2021 | 23/06/2021 | M/S B. ENTERPRISE | 4.28 | 4.28 | 100 | 0
92 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Dakshin Shibganj & Ramganga W/S Scheme at Pathar Pratima Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 08.06.2021 to 28.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000440/2021-2022 | 325/KSD | 02/06/2021 | 23/06/2021 | M/S B. ENTERPRISE | 4.41 | 4.41 | 100 | 0
93 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Kachuberia, Mandirtala & Krishnanagar W/S Scheme at Sagar Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Period from 08.06.2021 to 28.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000441/2021-2022 | 326/KSD | 02/06/2021 | 23/06/2021 | ANANTA KUMAR GIRI | 2.55 | 2.55 | 100 | 0
94 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Companirchar, Khasramkarchar & khansaheber Abad W/S Scheme at Sagar Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Period from 08.06.2021 to 28.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000442/2021-2022 | 327/KSD | 02/06/2021 | 23/06/2021 | GROWING CONCERN | 2.54 | 2.54 | 100 | 0
95 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Dakshin Shibganj W/S Scheme at Pathar Pratima Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 01.06.2021 to 07.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000446/2021-2022 | 206/KSD | 31/05/2021 | 07/06/2021 | M/S B. ENTERPRISE | 4.78 | 4.78 | 100 | 0
96 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Ramganga & Gurudaspur W/S Scheme at Pathar Pratima Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Period : 01.06.2021 to 07.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000447/2021-2022 | 207/KSD | 31/05/2021 | 07/06/2021 | M/S B. ENTERPRISE | 4.78 | 4.78 | 100 | 0
97 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I. water tanks from different running PWSS to the command area of Sumatinagar & Purusottampur W/S Scheme at Sagar Block affected due to Severe Cyclone YASS under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Period from 01.06.2021 to 07.06.2021) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000448/2021-2022 | 208/KSD | 31/05/2021 | 07/06/2021 | ANANTA KUMAR GIRI | 4.83 | 4.83 | 100 | 0
98 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I/PVC water tanks from nearby available drinking water source to the command area of Arunnagar Belpukuria, Dakshin Ramkrishnapur Zone-I, Dakshin Ramkrishnapur Zone-II and Dhola W/S Scheme within Kulpi Block, due to impending Cyclonic Storm "YAAS" under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001174/2021-2022 | 87/DHSD | 04/06/2021 | 19/06/2021 | M/S. JHARNA ENTERPRISE | 4.92 | 4.82 | 98 | 0
99 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in G.I/PVC water tanks from nearby available drinking water source to the command area of Birendra Bagaria, Iswaripur, Kulpi and Karanjali W/S Scheme within Kulpi Block, due to impending Cyclonic Storm "YAAS" under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001175/2021-2022 | 88/DHSD | 04/06/2021 | 19/06/2021 | M/S. R.M. CONSTRUCTION | 4.9 | 4.85 | 99 | 0
100 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in PVC water tanks at Kumirmari (Palamari Kheyaghat, Kumirmari Budhbar Bazar) of Gosaba Block affected due to 'YAAS' Cyclone under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001356/2021-2022 | 331/CSD | 15/06/2021 | 05/07/2021 | M/S. MIHIR KUMAR NASKAR | 1.99 | 1.99 | 100 | 0
101 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Supply of drinking water loaded in PVC water tanks at Lahiripur of Gosaba Block affected due to 'YAAS' Cyclone under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001358/2021-2022 | 332/CSD | 15/06/2021 | 05/07/2021 | M/S. MIHIR KUMAR NASKAR | 4.24 | 4.24 | 100 | 0
102 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Sinking of 02(Two) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 300 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Canning-I Block (Taldi G.P.-01 no, Nikarighata G.P.-01) due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A-II) | Assistant Engineer,HQ-I |  | ORD/001387/2021-2022 | 6139/AD | 21/02/2022 | 08/03/2022 | D.N. ENTERPRISE | 5.53 | 4.6 | 83.12 | 0
103 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Sinking of 16(Sixteen) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 300 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Canning-II Block (Deuli-I G.P-03 no, Atherobanki G.P-02 no,Tambuldaha-II G.P-04 no, Deuli-II G.P-03 nos,Sarengabad G.P-04 no) due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) | Assistant Engineer,HQ-I |  | ORD/001389/2021-2022 | 6141/AD | 21/02/2022 | 07/04/2022 | SANAM ENTERPRISE | 44.15 | 42.49 | 96.25 | 0
104 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Sinking of 06(Six) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 300 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Canning-II Block (Kalikatala G.P-03 no,Tambuldaha-I G.P-03 no) due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) | Assistant Engineer,HQ-I |  | ORD/001390/2021-2022 | 6142/AD | 21/02/2022 | 23/03/2022 | MAITY SUPPLIERS | 16.45 | 15.4 | 93.62 | 0
105 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Sinking of 07(Seven) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 300 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Patharpratima Block (Patharpratima G.P.- 02 no, Durbachati G.P.- 03 no,Gopalpur G.P-02 no) due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) | Assistant Engineer,HQ-I |  | ORD/001392/2021-2022 | 6144/AD | 21/02/2022 | 23/03/2022 | A.M. ENTERPRISE | 20.86 | 20.82 | 99.81 | 0
106 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Sinking of 03(Three) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 300 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Kakdwip Block (Ramgopalpur G.P.- 03 no) due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-A) | Assistant Engineer,HQ-I |  | ORD/001395/2021-2022 | 6146/AD | 21/02/2022 | 08/03/2022 | MD. FAZLUL ISLAM GAZI | 8.94 | 0 | 0 | 0
107 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Sinking of 03(Three) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 300 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Kakdwip Block (Rabindra G.P.- 03 no) due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-B) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001396/2021-2022 | 6147/AD | 21/02/2022 | 08/03/2022 | CAMELIA CONSTRUCTION | 8.94 | 8.89 | 99.45 | 0
108 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Sinking of 03(Three) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 300 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Kakdwip Block (Surjanagar G.P.- 03 no) due to affected by super Cyclone-"YAASH" in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-C) | Assistant Engineer,HQ-I |  | ORD/001398/2021-2022 | 6148/AD | 21/02/2022 | 08/03/2022 | CAMELIA CONSTRUCTION | 8.94 | 8.89 | 99.45 | 0
109 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Sinking of 05(Five) nos. 100mm x 50mm dia. having 5 nos. Strainer upto 330 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Namkhana Block (Namkhana G.P.-05 no) due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-A) | Assistant Engineer,HQ-I |  | ORD/001400/2021-2022 | 6149/AD | 21/02/2022 | 23/03/2022 | BABAMONI CONSTRUCTION | 15.94 | 15.7 | 98.51 | 0
110 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Sinking of 06(Six) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 330 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Namkhana Block (Frezerganj G.P.- 03 no, Shibrampur G.P.- 03 no) due to affected by super Cyclon-"YAASH" in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-C) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001405/2021-2022 | 6151/AD. | 21/02/2022 | 23/03/2022 | M/S. L.P. CONSTRUCTION | 19.13 | 0 | 0 | 0
111 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Sinking of 11(Eleven) nos. 1100mm x 50mm dia. having 4 nos. Strainer upto 300 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Kultali Block (Deulbari Debipur G.P.- 01 no, Gurguria Bhubaneswari G.P.- 01 no,Kundakhali Godabar G.P.- 01 no, Jalaberia-II G.P.- 01 no, Gopalgunj G.P.- 02 no, Maipith G.P.- 01 no, Merigunj-II G.P.- 01 no, Jalaberi-I G.P.- 02 no, Merigunj-I G.P.- 01 no) due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. | Assistant Engineer,HQ-I |  | ORD/001410/2021-2022 | 6154/AD | 21/02/2022 | 07/04/2022 | M/S. BOSE CONCERN | 32.77 | 31.94 | 97.45 | 0
112 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Sinking of 03 (Three) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 300 mtr (Average) depth fitted with India Mark-I I DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P .areas under Sagar Block (Ramkarchar G.P.- 03 no,) due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-A) | Assistant Engineer,HQ-I |  | ORD/001500/2021-2022 | 6261/AD | 24/02/2022 | 11/03/2022 | BIBEK MAITY | 10.54 | 0 | 0 | 0
113 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Sinking of 06(Six) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 300 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Sagar Block (D.S-II G.P.-06 no,) due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-B) | Assistant Engineer,HQ-I |  | ORD/001503/2021-2022 | 6262/AD | 24/02/2022 | 26/03/2022 | BIBEK MAITY | 21.09 | 0 | 0 | 0
114 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Sinking of 06(Six) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 300 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Sagar Block (Dhablat G.P.- 06 no) due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-C) | Assistant Engineer,HQ-I |  | ORD/001506/2021-2022 | 6263/AD | 24/02/2022 | 26/03/2022 | M/S. L.P. CONSTRUCTION | 21.09 | 0 | 0 | 0
115 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Sinking of 11(Eleven) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 350 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Basanti Block (Basanti G.P.- 02 no, Bharatghar G.P.- 01 no, Nafarjung G.P.- 01 no, Joyatishpur G.P.- 01 no, RC. Khali G.P.- 02 no, Amjhara G.P.- 02 no, Kathalberia G.P.- 02 no) due to affected by super Cyclone-"YAASH" in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001511/2021-2022 | 6267/AD | 24/02/2022 | 10/04/2022 | AKBAR ALI MOLLA | 36.08 | 34.36 | 95.25 | 0
116 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Sinking of 09(Nine) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 350 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Mathurapur-II Block (Khari G.P.- 02 no, Radhakanta Pur G.P.- 02 no, Dighirpar Bakultala G.P.- 01 no, Kautala G.P.-01 no, Kashinagar G.P.-01 no, Raidighi G.P.- 01 no, Gilarchat G.P.-01 no) due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. | Assistant Engineer,HQ-I |  | ORD/001512/2021-2022 | 6268/AD | 24/02/2022 | 26/03/2022 | AKBAR ALI MOLLA | 28.22 | 27.64 | 97.94 | 0
117 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Sinking of 05(Five) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 350 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Mathurapur - I Block (SankarPur G.P.- 01 no, Abad Bhagaban Pur G.P.- 01 no, Debi Pur G.P.- 01 no, Lal Pur G.P.- 01 no, Krishna Chandra Pur G.P.- 01 no,) due to affected by super Cyclon-"YAASH" in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. [ PART-A ] | Assistant Engineer,HQ-I |  | ORD/001513/2021-2022 | 6269/AD | 24/02/2022 | 26/03/2022 | MD. NAZRUL ISLAM GAZI | 15.43 | 13.27 | 86 | 0
118 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Sinking of 06(Six) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 350 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Mathurapur - I Block (Nalua G.P.- 01 no,Mathurapur Purba G.P-01 no,L.N.Pur Uttar G.P-01 no,Mathurapur Paschim G.P-01 no,L.N Pur Dakshin G.P-02 no) due to affected by super Cyclon-"YAASH" in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.[ PART-B] | Assistant Engineer,HQ-I |  | ORD/001514/2021-2022 | 6270/AD | 24/02/2022 | 26/03/2022 | MD. NAZRUL ISLAM GAZI | 18.56 | 15.57 | 83.89 | 0
119 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Sinking of 10(Ten) nos.100mm x 50mm dia. having 4 nos. Strainer upto 400 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Joynagar-II Block (Nalgora G.P.-01no, Chuprijhara G.P.-01no, Manirhat G.P.-01 no, Baishata G.P.-01no, Moydah G.P-02 nos,Futigoda G.P-01 nos,Gardewani G.P-01 no,Bele Durganagar G.P-02 no) due to affected by super Cyclon-"YAASH" in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. | Assistant Engineer,HQ-I |  | ORD/001515/2021-2022 | 6271/AD | 24/02/2022 | 10/04/2022 | M/S. S.D. CONSTRUCTION | 36.34 | 35.93 | 98.88 | 0
120 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Sinking of 03(Three) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 350 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Joynagar-I Block (Uttar Durgapur G.P.- 01 no, Sreepur G.P.- 01 no, Baharu G.P.-01 no,) due to affected by super Cyclon-"YAASH" in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. [ PART-B ] | Assistant Engineer,HQ-I |  | ORD/001517/2021-2022 | 6273/AD | 24/02/2022 | 11/03/2022 | MONDAL ENTERPRISE (NEW) | 9.17 | 8.77 | 95.57 | 0
121 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Sinking of 01(One) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 300 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Canning-I Block (Gopalpur G.P.-01 no) due to affected by super Cyclon-"YAASH" in the Dist. of South 24 Parganas under Alipore Division, PHE Dte.(PART-D) | Assistant Engineer, RWS |  | ORD/001577/2021-2022 | 899/RWS | 31/03/2022 | 15/04/2022 | DIPA CHHETRI | 2.79 | 2.67 | 95.67 | 0
122 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Sinking of 08 (Eight) nos. 100mm x 50mm dia. having 4 nos. Strainer upto 300 mtr (Average) depth fitted with India Mark-II DWP hand pump Tubewell with supplying PVC Pipe including High Rise Platforms and Stairs with G.I hand railing at different locations within different G.P.areas under Patharpratima Block (Sridharnagar G.P.- 03 no, Brajaballavpur G.P.- 02 no, Banashyamnagar G.P.- 03 no) due to affected by super Cyclone-YAASH in the Dist. of South 24 Parganas under Alipore Division, PHE Dte. (PART-C) | Assistant Engineer,HQ-I |  | ORD/001581/2021-2022 | 6961/AD | 29/03/2022 | 28/04/2022 | HARIDAS DUTTA | 28.12 | 28 | 99.57 | 0
123 | SOUTH 24 PARAGANAS |  | Alipore Division | Sinking of 228 nos. Mark - II hand pump Tubewells to mitigate the acute water scarcity due to super cyclone ''YAAS'' | SM/09436 | Disaster | Material Requisition To Resource Division |  |  | RTOR000006/2021-2022 | 5105/AD | 23/12/2021 |  | Resource Division | 36.63 | 0 | 0 | 0
Total | [13 empty] | 871.43 | 734.19 | 84.25