## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 07 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone- | SM/09470 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Gopalnagar 3 No. for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001744/2020-2021 | 1216/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.19 | 4.18 | 99.71 | 0
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 07 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone- | SM/09470 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Hari Mandir Para (Phase-I), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001759/2020-2021 | 1218/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.25 | 4.25 | 100 | 0
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 07 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone- | SM/09470 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Village :- Debnibus & Bijoybati of Debnibus W/S Scheme, Block -Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. Part-A | Assistant Engineer, Kakdwip Sub Division |  | ORD/001796/2020-2021 | 1236/KSD | 23/02/2021 | 05/03/2021 | SUMAN ENTERPRISE | 4.5 | 4.32 | 96.05 | 97
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 07 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone- | SM/09470 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mahendranagar (Paschim) (Part) & Purba Para (Part), for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001850/2020-2021 | 1281/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.27 | 4.27 | 100 | 0
5 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 07 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone- | SM/09470 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Village :- Debnibus & Bijoybati of Debnibus W/S Scheme, Block -Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. Part-B | Assistant Engineer, Kakdwip Sub Division |  | ORD/001853/2020-2021 | 1284/KSD | 23/02/2021 | 05/03/2021 | SUMAN ENTERPRISE | 4.46 | 4.13 | 92.49 | 86.5
6 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 07 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone- | SM/09470 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mahendranagar (Paschim) (Phase-II), for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001855/2020-2021 | 1286/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.28 | 4.28 | 100 | 0
7 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 07 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone- | SM/09470 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- 1 no. Block (Part) & 2 no. Block (Part), for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001857/2020-2021 | 1288/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.28 | 4.28 | 100 | 0
8 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 07 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone- | SM/09470 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- 4 no. Block (Part) & 5 no. Block (Part), for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001887/2020-2021 | 1309/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.28 | 4.28 | 100 | 0
9 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 07 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone- | SM/09470 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bangheri (Phase-III) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001917/2020-2021 | 1327/KSD | 23/02/2021 | 05/03/2021 | TAPAN DAS | 4.39 | 4.35 | 99.16 | 100
10 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 07 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone- | SM/09470 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Village :- Debnibus & Bijoybati of Debnibus W/S Scheme, Block -Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. Part-C | Assistant Engineer, Kakdwip Sub Division |  | ORD/001920/2020-2021 | 1330/KSD | 23/02/2021 | 05/03/2021 | SUMAN ENTERPRISE | 4.49 | 4.3 | 95.92 | 96
11 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 07 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone- | SM/09470 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- 5 no. Block (Part) & Dakshin Gopalnagar 3 no. (Part), for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001922/2020-2021 | 1333/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.27 | 4.27 | 100 | 0
12 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 07 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone- | SM/09470 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- 2 no. Block (Part) & 4 no. Block (Part), for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001924/2020-2021 | 1336/KSD | 23/02/2021 | 05/03/2021 | M/S B. ENTERPRISE | 4.28 | 4.28 | 100 | 0
13 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 07 (seven) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Paschim Surendranagar (Zone- | SM/09470 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000776/2023-2024 | 610/AD | 29/01/2024 |  | Resource Division | 9.27 | 0 | 0 | 0
Total | [13 empty] | 61.2 | 51.18 | 83.63