## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Debnibus W/S Scheme inclu | SM/09471 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to the households of Village :- Debnibus & Bijoybati of Debnibus W/S Scheme, Block -Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. Part-D (2nd Call) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000155/2021-2022 | 408/KSD | 07/07/2021 | 22/07/2021 | M/S KALIPADA JANA | 4.49 | 4.09 | 91.01 | 100
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Debnibus W/S Scheme inclu | SM/09471 | Retrofitting | Surging of 2 no. Big dia Tubewell under Debnibus Water Supply Scheme under JJM, Block - Namkhana under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000598/2022-2023 | 5923/AD | 19/10/2022 | 03/11/2022 | S.K.GOLUI | 6.1 | 6.1 | 100 | 100
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Debnibus W/S Scheme inclu | SM/09471 | Retrofitting | Operation and maintenance of distribution system including rising main for Debnibus Piped Water Supply Scheme of Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. [Period from 01.12.2021 to 30.11.2022] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000908/2021-2022 | 768/KSD | 29/11/2021 | 24/11/2022 | ANANTA KUMAR GIRI | 4.75 | 0 | 0 | 100
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Debnibus W/S Scheme inclu | SM/09471 | Retrofitting | Route Survey for Providing FHTC at Debnibus W/S Scheme & it's adjacent areas, Block Namkhana under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001031/2021-2022 | 541/KSD | 01/09/2021 | 21/09/2021 | LEMNISCATE | 4.59 | 4.53 | 98.62 | 100
5 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Debnibus W/S Scheme inclu | SM/09471 | Retrofitting | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Debnibus W/S Scheme & it's adjacent areas, Block - Namkhana under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001048/2021-2022 | 2287/AD | 07/09/2021 | 14/09/2021 | INDRANIL DUTTA & ASSOCIATES | 3.34 | 3.34 | 100 | 100
6 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Debnibus W/S Scheme inclu | SM/09471 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000287/2023-2024 | 3083/AD | 28/09/2023 |  | Resource Division | 0.3 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) to the households for 18 (eighteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Debnibus W/S Scheme inclu | SM/09471 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000546/2023-2024 | 10/AD | 02/01/2024 |  | Resource Division | 17.88 | 0 | 0 | 0
Total | [13 empty] | 41.45 | 18.06 | 43.56