## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Providing Functional Household Tap Connection (FHTC) to all the households in Diamon Harbour II Zone V including Operation and Maintenance of scheme for 01 (one) year under Mega Surface Water based water supply scheme for Falta Mathurapur, District South | SM/09505 | Retrofitting | Laying distribution system in left out portion for 100% coverage of Functional Household Tap Connection (FHTC) at Kandalia, Sundarika, Parashurampur and Gopalpur villages due to Swajal Gram activities under Zone-V of Diamond Harbour-II within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000580/2022-2023 | 5856/AD | 18/10/2022 | 17/11/2022 | M/S SAMADDAR CONSTRUCTION | 91.55 | 39 | 42.6 | 60
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Providing Functional Household Tap Connection (FHTC) to all the households in Diamon Harbour II Zone V including Operation and Maintenance of scheme for 01 (one) year under Mega Surface Water based water supply scheme for Falta Mathurapur, District South | SM/09505 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Diamond Harbour-II Zone-V including Operation and Maintenance of scheme for 01 (one) year under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas Block Diamond Harbour-II, under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001337/2021-2022 | 6018/AD | 15/02/2022 | 15/02/2023 | M/S A.K. GHATAK | 185.19 | 171.49 | 92.6 | 100
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Providing Functional Household Tap Connection (FHTC) to all the households in Diamon Harbour II Zone V including Operation and Maintenance of scheme for 01 (one) year under Mega Surface Water based water supply scheme for Falta Mathurapur, District South | SM/09505 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000069/2022-2023 | 4969/AD | 16/09/2022 |  | Resource Division | 9.24 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Providing Functional Household Tap Connection (FHTC) to all the households in Diamon Harbour II Zone V including Operation and Maintenance of scheme for 01 (one) year under Mega Surface Water based water supply scheme for Falta Mathurapur, District South | SM/09505 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000097/2022-2023 | 7495/AD | 26/11/2022 |  | Resource Division | 3.52 | 0 | 0 | 0
Total | [13 empty] | 289.5 | 210.48 | 72.71