## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Debipur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal | SM/09511 | Retrofitting | Supply and delivery at site of different dia. Specials in connection with laying distribution system of piped water supply at Zone - II (Debipur PWSS) Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000609/2023-2024 | 240/RSD | 22/08/2023 | 21/09/2023 | DIPTI ENTERPRISE | 0.96 | 0.96 | 100 | 99
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Debipur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal | SM/09511 | Retrofitting | Parallel distribution pipeline to provide FHTC at Debipur moza under Zone-II of Mathurapur-I block, under Surface water based water supply scheme Falta- Mathurapur of Raidighi Sub-Division under Alipore Division, PHE Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001135/2022-2023 | 600/RSD | 23/12/2022 | 22/01/2023 | SANKAR HALDER | 4.76 | 4.76 | 100 | 99
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Debipur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal | SM/09511 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Debipur piped water supply scheme ( Mathurapur-I, Zone-II) including Operation and Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) (2nd call) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001197/2021-2022 | 5724/AD | 31/01/2022 | 31/01/2023 | M/S. JHARNA ENTERPRISE | 101.84 | 52.13 | 51.19 | 85
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Debipur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal | SM/09511 | Retrofitting | Protection and other ancillary work (Node No. 2-30, 28-26, 25-23, 21-22, 17-19) for laying distribution system and providing FHTC at Zone - II Block of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) under under Mega surface water based water supply scheme-Falta Mathurapur under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001799/2022-2023 | 930/RSD | 10/03/2023 | 09/04/2023 | DIPTI ENTERPRISE | 4.27 | 3.99 | 93.51 | 99
5 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Debipur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal | SM/09511 | Retrofitting | Construction of 500 cum capacity 20 M. staging height RCC Over Head Water Reservoir as per departmental drawing & specification incl. RCC Bored Pile & Pile Cap upto pedestal at Mathurapur - I Block (Zn. - II) for Mega Surface Water Based Water Supply Scheme of Falta - Mathurapur South 24 Pgs. under Raidighi Sub Divn. of Alipore Division, PHE dte. |  |  | ORD/002025/2019-2020 | 7721/AD | 26/02/2020 | 24/02/2025 | G.B. CONSTRUCTION & CO. | 64.12 | 0 | 0 | 75
6 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Debipur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal | SM/09511 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 3450/AD | 25/07/2022 |  | Resource Division | 45.51 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Debipur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal | SM/09511 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000035/2022-2023 | 3588/AD | 29/07/2022 |  | Resource Division | 3.28 | 0 | 0 | 0
Total | [13 empty] | 224.73 | 61.84 | 27.52