## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Mathurapur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & | SM/09514 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Mathurapur piped water supply scheme ( Mathurapur-I, Zone-VII) including Operation and Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Raidighi sub division |  | ORD/000569/2021-2022 | 3670/AD | 22/11/2021 | 22/11/2022 | M/S. J.K. TRIPATHI & SONS | 80.12 | 72.52 | 90.52 | 100
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Mathurapur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & | SM/09514 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000036/2021-2022 | 6636/AD | 15/03/2022 |  | Resource Division | 326.7 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Mathurapur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & | SM/09514 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000605/2023-2024 | 235/AD | 11/01/2024 |  | Resource Division | 11.33 | 0 | 0 | 0
Total | [13 empty] | 418.15 | 72.52 | 17.34