## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) | SM/09515 | Retrofitting | Extension of pipeline to provide Functional Household Tap Connection (FHTC) and construction of sluice valve chamber under Krishnarampur water supply scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000219/2022-2023 | 3060/AD | 13/07/2022 | 12/08/2022 | KAKALI ENTERPRISE | 8.06 | 8.03 | 99.61 | 100
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) | SM/09515 | Retrofitting | Providing Functional Household Tap Connection (FHTC) to all the households in Krishnarampur piped water supply scheme ( Mathurapur-I, Zone-X) including Operation & Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) (2nd call) | Assistant Engineer, Raidighi sub division |  | ORD/001199/2021-2022 | 5725/AD | 31/01/2022 | 31/01/2023 | SUPRITI ENTERPRISE | 106.12 | 62.91 | 59.28 | 100
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Krishnarampur piped water supply scheme, Mathurapur-I block in the district South 24 Parganas for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) | SM/09515 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000081/2022-2023 | 5552/AD | 29/09/2022 |  | Resource Division | 4.08 | 0 | 0 | 0
Total | [13 empty] | 118.26 | 70.94 | 59.99