## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-V, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme fo | SM/09558 | Retrofitting | Providing FHTC including distribution system and other allied works at Zone- V of Mathurapur-I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 4138 ] | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000087/2023-2024 | 498/AD | 11/05/2023 | 09/08/2023 | JAL PRAVAHIKA PVT. LTD. | 569.23 | 8.07 | 1.42 | 41
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-V, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme fo | SM/09558 | Retrofitting | Construction of 700M3 capacity 20m straging height R.C.C OHR as per departmental design drawing & specification including R.C.C. bored pile & pile cap upto pedestal at Mathurapur-I block zone- v Site for Mega surface water based water supply scheme for Falta Mathurapur project under Raidighi Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002152/2019-2020 | 7722/AD | 26/02/2020 |  | JAL PRAVAHIKA PVT. LTD. | 128.67 | 57.9 | 45 | 80
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-V, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme fo | SM/09558 | Retrofitting | Protection of pipeline at Zone -V Mathurapur -I block under Raidighi Sub Division of Alipore Division, PHE Dte. (Tender no.- Not found) | Assistant Engineer, Raidighi sub division |  | ORD/002164/2019-2020 | 681/RSD | 03/01/2020 |  | M/S MAA ENTERPRISE | 4.63 | 4.63 | 100 | 100
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-V, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme fo | SM/09558 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000599/2023-2024 | 231/AD | 11/01/2024 |  | Resource Division | 24.54 | 0 | 0 | 0
Total | [13 empty] | 727.06 | 70.6 | 9.71