## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 15 (Fifteen) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Sagar Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.06.2021 to 31.08.2021] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000078/2021-2022 | 555/AD | 28/05/2021 | 26/08/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.6 | 3.6 | 100 | 0
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 14 (Fourteen) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Sagar Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.06.2021 to 31.08.2021] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000079/2021-2022 | 556/AD | 28/05/2021 | 26/08/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.36 | 3.36 | 100 | 0
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 12 (Twelve) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Sagar Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.06.2021 to 31.08.2021] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000080/2021-2022 | 557/AD | 28/05/2021 | 26/08/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 2.88 | 2.88 | 100 | 0
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 17 (Seventeen) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Kakdwip Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.06.2021 to 31.08.2021] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000081/2021-2022 | 558/AD | 28/05/2021 | 26/08/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.08 | 4.08 | 100 | 0
5 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 16 (Sixteen) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Kakdwip Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.06.2021 to 31.08.2021] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000082/2021-2022 | 559/AD | 28/05/2021 | 26/08/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.84 | 3.84 | 100 | 0
6 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 15 (Fifteen) nos. Integrated Water Supply Scheme damaged due to super cyclonem"AMPHAN-2020" at different Schools (as per enclosed list) under Kakdwip Block of Kakdwip Sub-Division undermAlipore Division, P.H.E. Dte. [Period from 01.06.2021 to 31.08.2021] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000083/2021-2022 | 560/AD | 28/05/2021 | 26/08/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.6 | 3.6 | 100 | 0
7 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 24 (Twenty four) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Pathar Pratima Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.06.2021 to 31.08.2021]. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000084/2021-2022 | 561/AD | 28/05/2021 | 26/08/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 5.76 | 5.76 | 100 | 0
8 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 29 (Twenty nine) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Pathar Pratima Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.06.2021 to 31.08.2021] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000085/2021-2022 | 562/AD | 28/05/2021 | 26/08/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 6.96 | 6.96 | 100 | 0
9 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 27 (Twenty seven) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Pathar Pratima Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.06.2021 to 31.08.2021] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000086/2021-2022 | 563/AD | 28/05/2021 | 26/08/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 6.48 | 6.48 | 100 | 0
10 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 26 (Twenty six) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Pathar Pratima Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.06.2021 to 31.08.2021] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000087/2021-2022 | 564/AD | 28/05/2021 | 26/08/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 6.24 | 6.24 | 100 | 0
11 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 24 (Twenty four) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Pathar Pratima Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.09.2021 to 30.11.2021]. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000319/2021-2022 | 1907/AD | 27/08/2021 | 25/11/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 5.76 | 5.76 | 100 | 0
12 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 29 (Twenty nine) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Pathar Pratima Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.09.2021 to 30.11.2021]. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000320/2021-2022 | 1910/AD | 27/08/2021 | 25/11/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 6.96 | 6.96 | 100 | 0
13 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 26 (Twenty Six) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Pathar Pratima Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.09.2021 to 30.11.2021]. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000321/2021-2022 | 1908/AD | 27/08/2021 | 25/11/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 6.24 | 6.24 | 100 | 0
14 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 27 (Twenty seven) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Pathar Pratima Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.09.2021 to 30.11.2021]. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000322/2021-2022 | 1909/AD | 27/08/2021 | 25/11/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 6.48 | 6.48 | 100 | 0
15 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 14 (Fourteen) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Kakdwip Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.09.2021 to 30.11.2021]. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000331/2021-2022 | 1911/AD | 27/08/2021 | 25/11/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.36 | 3.36 | 100 | 0
16 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 15 (Fifteen) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Kakdwip Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.09.2021 to 30.11.2021]. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000333/2021-2022 | 1912/AD | 27/08/2021 | 25/11/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.6 | 3.6 | 100 | 0
17 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 16 (Sixteen) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Kakdwip Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.09.2021 to 30.11.2021]. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000334/2021-2022 | 1913/AD | 27/08/2021 | 25/11/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.84 | 3.84 | 100 | 0
18 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 17 (Seventeen) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Kakdwip Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.09.2021 to 30.11.2021]. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000337/2021-2022 | 1921/AD | 27/08/2021 | 25/11/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.08 | 4.08 | 100 | 0
19 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 12 (Twelve) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Sagar Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.09.2021 to 30.11.2021]. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000342/2021-2022 | 1922/AD | 27/08/2021 | 25/11/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 2.88 | 2.88 | 100 | 0
20 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 14 (Fourteen) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Sagar Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.09.2021 to 30.11.2021]. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000343/2021-2022 | 1923/AD | 27/08/2021 | 25/11/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.36 | 3.36 | 100 | 0
21 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 15 (Fifteen) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Sagar Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.09.2021 to 30.11.2021] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000344/2021-2022 | 1924/AD | 27/08/2021 | 25/11/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.6 | 3.6 | 100 | 0
22 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Immediate restoration/ maintenance work of Nandarampur W/S Scheme under Mathurapur-II block in connection with Cyclone Amphan at Raidighi Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001203/2020-2021 | 231/B/AD | 01/06/2020 |  | TIYASHA ENTERPRISE | 6.01 | 6.01 | 100 | 0
23 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Immediate restoration/ maintenance work of Nandakumarpur W/S Scheme under Mathurapur-I block in connection with Cyclone Amphan at Raidighi Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001244/2020-2021 | 170/B/AD. | 24/05/2020 |  | TIYASHA ENTERPRISE | 6.64 | 6.64 | 100 | 0
24 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | SINKING OF 27 (TWENTY SEVEN) NOS. 100MM X 50MM DIA HAVING 4 NOS. STRAINER UPTO 300 MTR. DEPTH FITTED WITH INDIA MARK-II DWP HAND PUMP TWL WITH SUPPLYING PVC PIPE AT DIFF LOCATION WITHIN DIFF GP AREAS (DAKSHIN RAIPUR GP-27 NO) UNDER BUDGE BUDGE II BLOCK DUE TO AFFECTED BY SUPER CYCLONE AMPHAN IN THE DIST. OF S24PGS OF ALIPORE DIVISION, PHE DTE. |  |  | ORD/001251/2020-2021 | 766/AD | 16/07/2020 |  | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 58.34 | 0 | 0 | 0
25 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Protection of pipeline which are hanging due to erosion of sub-soil caused by Super Cyclone ' AMPHAN' at 6 no. Goranbose under Goranbose W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001355/2020-2021 | 1187/CSD | 15/12/2020 | 30/12/2020 | SUJIT KUMAR GHOSH | 4.85 | 4.82 | 99.52 | 0
26 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | IMMEDIATE REPLACEMENT OF DAMAGED 1 HP CAPACITY DC SOLAR PHOTOVOLTAIC SUBMERSSIBLE PUMP SET ,PUMP CONTROLLER 450WATT PEAK CAPACITY SOLAR PHOTOVOLTIC ARRAY PANEL AND ELECTRI CABLE 3 CORE 4 SQM BY NEW ONE INCL SUPPLYING TO SITE FIXING AND RETURN BACK THE DAMAGED PUMP TO THE SD STORE INCL TRANSPORTATION CHARGES OF ROAD WAYS AS WATER WAYS LABOUR CHARGES OF WITHDRAWAL OF THE DAMAGED ONE AND LOWERING OF THE NEW ONE AND MTC FOR THE DURATION OF 2 MONTHS FROM THE INSTL DATE FOR URGENT RESTORATION OF INTEGRATED W/S SCHEME DUE TO AFFECTED BY SUPER CYCLONE AMPHAN IN THE DIST. OF S24PGS UNDER RSD SD OF ALIPORE DIVISION, PHE DTE. |  |  | ORD/001498/2020-2021 | 193/A/AD | 28/05/2020 |  | MAHAVIR PUMPS MANUFACTURING PVT. LTD | 28.74 | 28.74 | 100 | 0
27 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | SINKING OF 01 (ONE) NOS. 100MM X 50MM DIA HAVING 4 NOS. STRAINER UPTO 330 MTR. DEPTH FITTED WITH INDIA MARK-II DWP HAND PUMP TWL WITH SUPPLYING PVC PIPE AT DIFF LOCATIONS WITHIN GOKORNEE GP (PART-A) AREAS UNDER MAGRAHAT-II BLOCK DUE TO AFFECTED BY SUPER CYCLONE AMPHAN IN THE DIST. OF S24PGS OF ALIPORE DIVISION, PHE DTE.[PART-A] |  |  | ORD/001505/2020-2021 | 1096/AD | 30/07/2020 |  | MAMONI CONSTRUCTION | 2.33 | 2.33 | 100 | 0
28 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Relaying damaged pipeline and protection work due to Super Cyclone ' AMPHAN' within node 20-21, 119,120, 33-34, 44-45, 3-142, 197-198, 143-160 & others at Garanbose W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001564/2020-2021 | 1057/CSD | 27/11/2020 | 27/12/2020 | SUJIT KUMAR GHOSH | 4.84 | 3.2 | 66.07 | 0
29 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Additional work of construction of boundary wall damaged by Cyclone 'AMPHAN' at Head Work site of Dharmatala W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001569/2020-2021 | 974/CSD | 09/11/2020 | 09/12/2020 | GOUTAM HALDAR (I) | 2.58 | 1.03 | 40.09 | 0
30 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Relaying damaged pipeline and protection work due to Super Cyclone ' AMPHAN' within node 30-31, 168-169, 209-210, 105-106 & others at Garanbose W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001580/2020-2021 | 1065/CSD | 27/11/2020 | 27/12/2020 | SUJIT KUMAR GHOSH | 4.84 | 2.72 | 56.3 | 0
31 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Supply of drinking water loaded in G.I/PVC water tanks from nearby available drinking water source to the command area of Dwariknagar, Mosat, Kanpur, Mongrajpur, Boria, Atkrishnarampur and Lakshmipur w/s scheme within Diamond Harbour - I block affected due to AMPHAN Cyclone under Diamond Harbour sub division of Alipore Division PHE Dte. |  |  | ORD/001963/2020-2021 | 169/D/AD | 22/05/2020 |  | M/S. SUMAN ENTERPRISE | 10.51 | 10.51 | 100 | 0
32 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 24 (Twenty four) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Pathar Pratima Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.03.2021 to 31.05.2021] | Assistant Engineer, Kakdwip Sub Division |  | ORD/002050/2020-2021 | 5505/AD | 26/02/2021 | 27/05/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 5.76 | 5.76 | 100 | 0
33 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 26 (Twenty six) nos. Integrated Water Supply Scheme damaged due to supercyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Pathar Pratima Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.03.2021 to 31.05.2021] | Assistant Engineer, Kakdwip Sub Division |  | ORD/002051/2020-2021 | 5506/AD | 26/02/2021 | 27/05/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 6.24 | 6.24 | 100 | 0
34 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 27 (Twenty seven) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Pathar Pratima Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.03.2021 to 31.05.2021] | Assistant Engineer, Kakdwip Sub Division |  | ORD/002052/2020-2021 | 5507/AD | 26/02/2021 | 27/05/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 6.48 | 6.48 | 100 | 0
35 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 29 (Twenty nine) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Pathar Pratima Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.03.2021 to 31.05.2021] | Assistant Engineer, Kakdwip Sub Division |  | ORD/002053/2020-2021 | 5508/AD | 26/02/2021 | 27/05/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 6.96 | 6.96 | 100 | 0
36 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 14 (Fourteen) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Kakdwip Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.03.2021 to 31.05.2021]. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002054/2020-2021 | 5509/AD | 26/02/2021 | 27/05/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.36 | 3.36 | 100 | 0
37 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 15 (Fifteen) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Kakdwip Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.03.2021 to 31.05.2021] | Assistant Engineer, Kakdwip Sub Division |  | ORD/002055/2020-2021 | 5510/AD | 26/02/2021 | 27/05/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.6 | 3.6 | 100 | 0
38 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 16 (Sixteen) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Kakdwip Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.03.2021 to 31.05.2021] | Assistant Engineer, Kakdwip Sub Division |  | ORD/002056/2020-2021 | 5511/AD | 26/02/2021 | 27/05/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.84 | 3.84 | 100 | 0
39 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 17 (Seventeen) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Kakdwip Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.03.2021 to 31.05.2021] | Assistant Engineer, Kakdwip Sub Division |  | ORD/002057/2020-2021 | 5512/AD | 26/03/2021 | 24/06/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.08 | 4.08 | 100 | 0
40 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 12 (Twelve) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Sagar Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.03.2021 to 31.05.2021] | Assistant Engineer, Kakdwip Sub Division |  | ORD/002058/2020-2021 | 5513/AD | 26/02/2021 | 27/05/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 2.88 | 2.88 | 100 | 0
41 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 14 (Fourteen) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Sagar Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.03.2021 to 31.05.2021] | Assistant Engineer, Kakdwip Sub Division |  | ORD/002059/2020-2021 | 5514/AD | 26/02/2021 | 27/05/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.36 | 3.36 | 100 | 0
42 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repair and maintenance of 15 (Fifteen) nos. Integrated Water Supply Scheme damaged due to super cyclone "AMPHAN-2020" at different Schools (as per enclosed list) under Sagar Block of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. [Period from 01.03.2021 to 31.05.2021] | Assistant Engineer, Kakdwip Sub Division |  | ORD/002060/2020-2021 | 5515/AD | 26/02/2021 | 27/05/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.6 | 3.6 | 100 | 0
43 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Repairing of damaged pipeline due to Bulbul from NH of Harihar Mondal to Gangarampur More at Sadhupur W/S Scheme block Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. |  |  | ORD/002147/2019-2020 | 992/CSD | 15/11/2019 |  | GANGA TUBEWELL AND HARDWARE | 3.42 | 3.42 | 100 | 0
44 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Repairing of damaged pipeline due to Bulbul at Kumirmari W/S Scheme block Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. |  |  | ORD/002148/2019-2020 | 991/CSD | 15/11/2019 |  | GANGA TUBEWELL AND HARDWARE | 3.75 | 3.75 | 100 | 0
45 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Repairing of damaged pipeline due to Bulbul at Sadhupur W/S Scheme block Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. |  |  | ORD/002149/2019-2020 | 986/CSD | 13/11/2019 |  | GANGA TUBEWELL AND HARDWARE | 4.72 | 4.72 | 100 | 0
46 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Immediate restoration/ maintenance work of Nandakumarpur W/S Scheme under Mathurapur-I block in connection with Cyclone Amphan at Raidighi Sub-Division of Alipore Division, PHE Dte. |  |  | ORD/002455/2020-2021 | 170/A/AD. | 24/05/2020 |  | TIYASHA ENTERPRISE | 5.53 | 5.53 | 100 | 0
47 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Immediate supply delivery of different spare parts at Sub-Divisional store/Head Work Site as may be required for urgent restoration of Integrated W/S Scheme under Joynagar-I&II block in connection with Cyclone Amphan at Raidighi Sub-Division of Alipore Division, PHE Dte |  |  | ORD/002456/2020-2021 | 235/B/AD | 02/06/2020 |  | MAHAVIR PUMPS MANUFACTURING PVT. LTD | 6.09 | 6.09 | 100 | 0
48 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | SINKING OF 15 NOS. 100MM X 50MM DIA HAVING 4 NOS. STRAINER UPTO 300 MTR. DEPTH FITTED WITH INDIA MARK-II DWP HAND PUMP TWL WITH SUPPLYING PVC PIPE AT BARUIPUR DEV. BLOCK DUE TO AFFECTED BY SUPER CYCLONE AMPHAN IN THE DIST. OF S 24PGS UNDER ALIPORE DIVISION, PHE DTE. |  |  | ORD/002463/2020-2021 | 1199/4/AD | 31/07/2020 |  | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 32.5 | 7.99 | 24.59 | 0
49 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Sinking of 02 nos. 100 mm x 50 mm dia having 04 nos. strainer upto 300 mtr. depth fitted with India Mark-II DWP Hand Pump Tubewell with supplying of PVC Pipe at Bishnupur-I block in connection with Amphan Cyclone under Alipore Division, PHE Dte. |  |  | ORD/002475/2020-2021 | 561/AD | 02/07/2020 |  | SRIJON ENTERPRISE | 4.2 | 4.2 | 100 | 0
50 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Sinking of 10 nos. 100 mm x 50 mm dia. having 04 nos. strainers upto 300 mtr. depth fitted with India Mark-II DWP Hand Pump Tubewell with supplying of PVC Pipe at Canning-I & Canning-II block due to affected by super cyclone Amphan under Canning Sub-Division of Alipore Division, PHE Dte. |  |  | ORD/003059/2020-2021 | 1201/AD | 31/07/2020 |  | GANGA TUBEWELL AND HARDWARE | 19.33 | 19.33 | 100 | 0
51 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Sinking of 31 nos. 100 mm x 50 mm dia having 04 nos. strainer upto 350 mtr. depth fitted with India Mark-II DWP Hand Pump at different location of Joynagar-I block unde Alipore Division, PHE Dte. |  |  | ORD/003066/2020-2021 | 1192/AD | 31/07/2020 |  | SUDIPTA BOSE | 75.54 | 45.54 | 60.29 | 0
52 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Sinking of 02 nos. 100 mm x 50 mm dia. having 04 nos. strainers upto 300 mtr. depth fitted with India Mark-II DWP Hand Pump Tubewell with supplying of PVC Pipe at Canning -II block due to affected by super cyclone Amphan under Alipore Division, PHE Dte. |  |  | ORD/003119/2020-2021 | 1140/AD | 30/07/2020 |  | SOHAM ENTERPRISE | 4.19 | 4.19 | 100 | 0
53 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Sinking of 02 nos. 100 mm x 50 mm dia. having 04 nos. strainers upto 300 mtr. depth fitted with India Mark-II DWP Hand Pump Tubewell with supplying of PVC Pipe at Canning -II block due to affected by super cyclone Amphan under Alipore Division, PHE Dte. |  |  | ORD/003120/2020-2021 | 1139/AD | 30/07/2020 |  | SOHAM ENTERPRISE | 4.09 | 4.09 | 100 | 0
54 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Sinking of 02 nos. 100 mm x 50 mm dia. having 04 nos. strainers upto 300 mtr. depth fitted with India Mark-II DWP Hand Pump Tubewell with supplying of PVC Pipe at Canning -II block due to affected by super cyclone Amphan under Alipore Division, PHE Dte. |  |  | ORD/003121/2020-2021 | 1120/AD | 30/07/2020 |  | SOHAM ENTERPRISE | 2.22 | 2.22 | 100 | 0
55 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Sinking of 02 nos. 100 mm x 50 mm dia. having 04 nos. strainers upto 300 mtr. depth fitted with India Mark-II DWP Hand Pump Tubewell with supplying of PVC Pipe at Canning -II block due to affected by super cyclone Amphan under Alipore Division, PHE Dte. |  |  | ORD/003122/2020-2021 | 1121/AD | 30/07/2020 |  | SOHAM ENTERPRISE | 2.22 | 2.22 | 100 | 0
56 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Sinking of 02 nos. 100 mm x 50 mm dia. having 04 nos. strainers upto 300 mtr. depth fitted with India Mark-II DWP Hand Pump Tubewell with supplying of PVC Pipe at Canning -II block due to affected by super cyclone Amphan under Alipore Division, PHE Dte. |  |  | ORD/003123/2020-2021 | 1124/AD | 30/07/2020 |  | SOHAM ENTERPRISE | 4.05 | 4.05 | 100 | 0
57 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Sinking of 02 nos. 100 mm x 50 mm dia. having 04 nos. strainers upto 300 mtr. depth fitted with India Mark-II DWP Hand Pump Tubewell with supplying of PVC Pipe at Canning -II block due to affected by super cyclone Amphan under Alipore Division, PHE Dte. |  |  | ORD/003124/2020-2021 | 1126/AD | 30/07/2020 |  | SOHAM ENTERPRISE | 4.15 | 4.15 | 100 | 0
58 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Sinking of 02 nos. 100 mm x 50 mm dia. having 04 nos. strainers upto 300 mtr. depth fitted with India Mark-II DWP Hand Pump Tubewell with supplying of PVC Pipe at Canning -II block due to affected by super cyclone Amphan under Alipore Division, PHE Dte. |  |  | ORD/003125/2020-2021 | 1115/AD | 30/07/2020 |  | SOHAM ENTERPRISE | 4.22 | 4.22 | 100 | 0
59 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Sinking of 02 nos. 100 mm x 50 mm dia. having 04 nos. strainers upto 300 mtr. depth fitted with India Mark-II DWP Hand Pump Tubewell with supplying of PVC Pipe at Canning -II block due to affected by super cyclone Amphan under Alipore Division, PHE Dte. |  |  | ORD/003126/2020-2021 | 1122/AD | 30/07/2020 |  | SOHAM ENTERPRISE | 0.98 | 0.98 | 100 | 0
60 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Sinking of 02 nos. 100 mm x 50 mm dia. having 04 nos. strainers upto 300 mtr. depth fitted with India Mark-II DWP Hand Pump Tubewell with supplying of PVC Pipe at Canning -II block due to affected by super cyclone Amphan under Alipore Division, PHE Dte. |  |  | ORD/003127/2020-2021 | 1119/AD | 30/07/2020 |  | SOHAM ENTERPRISE | 4.16 | 4.16 | 100 | 0
61 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Sinking of 02 nos. 100 mm x 50 mm dia. having 04 nos. strainers upto 300 mtr. depth fitted with India Mark-II DWP Hand Pump Tubewell with supplying of PVC Pipe at Canning -II block due to affected by super cyclone Amphan under Alipore Division, PHE Dte. |  |  | ORD/003128/2020-2021 | 1118/AD | 30/07/2020 |  | SOHAM ENTERPRISE | 4.12 | 4.12 | 100 | 0
62 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Sinking of 02 nos. 100 mm x 50 mm dia. having 04 nos. strainers upto 300 mtr. depth fitted with India Mark-II DWP Hand Pump Tubewell with supplying of PVC Pipe at Canning -II block due to affected by super cyclone Amphan under Alipore Division, PHE Dte. |  |  | ORD/003129/2020-2021 | 1117/AD | 30/07/2020 |  | SOHAM ENTERPRISE | 4.15 | 4.15 | 100 | 0
63 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Supply of drinking water loaded in PVC Water tanks from different P.W.S.S. to various location affected due to Amphan Cyclone under Canning Sub-Division of Alipore Division, PHE Dte. |  |  | ORD/003166/2020-2021 | 105/CSD | 20/05/2020 |  | SWASTIK CONSTRUCTION | 2 | 2 | 100 | 0
64 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repairing of (CI/DI/AC/UPVC) Rising main & distribution system for damaged due to Amphan Cyclone at Chunakhali W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte. |  |  | ORD/003167/2020-2021 | 138/CSD | 01/06/2020 |  | M/S M.G.CONSTRUCTION | 4.5 | 4.49 | 99.74 | 0
65 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repairing of (CI/DI/AC/UPVC) Rising main & distribution system for damaged due to Amphan Cyclone at Chunakhali W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte. |  |  | ORD/003168/2020-2021 | 303/AD | 05/06/2020 |  | M/S M.G.CONSTRUCTION | 7.3 | 7.24 | 99.19 | 0
66 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repairing of (CI/DI/AC/UPVC) Rising main & distribution system for damaged due to Amphan Cyclone at Adhia W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte. |  |  | ORD/003169/2020-2021 | 170/U/AD | 23/05/2020 |  | SUKANTA HALDER | 6.9 | 3.88 | 56.26 | 0
67 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repairing of (CI/DI/AC/UPVC) Rising main & distribution system for damaged due to Amphan Cyclone at Kalaria W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte. |  |  | ORD/003170/2020-2021 | 153/CSD | 04/06/2020 |  | ASHIS ENTERPRISE | 4.61 | 3.6 | 77.96 | 0
68 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repairing of (CI/DI/AC/UPVC) Rising main & distribution system for damaged due to Amphan Cyclone at Kalaria W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte |  |  | ORD/003171/2020-2021 | 170/R/AD | 23/05/2020 |  | SUKANTA HALDER | 6.9 | 5.93 | 85.99 | 0
69 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repairing of (CI/DI/AC/UPVC) Rising main & distribution system for damaged due to Amphan Cyclone at Goran Bose W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte |  |  | ORD/003172/2020-2021 | 170/W/AD | 23/05/2020 |  | RAMEN GHOSH | 9.23 | 8.76 | 94.91 | 0
70 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special repairing & maintenance of (CI/DI/AC/UPVC) Rising main & distribution system for damaged due to AMPHAN Cyclone at Chatrakhali W/S Scheme under Basanti block and Moukhali Kumarkhali W/S Scheme (Zone-I) under Canning II under Canning Sub-Division of Alipore Division, PHE Dte. |  |  | ORD/003173/2020-2021 | 170/Q/AD | 23/05/2020 |  | GANGA TUBEWELL AND HARDWARE | 6.08 | 4.81 | 79.14 | 0
71 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special urgent repairing of CI/DI/AC/UPVC Rising main distribution system for damaged due to AMPHAN Cyclone at Atharabeki W/S Scheme under Canning-II block under Canning Sub-Division of Alipore Division, PHE Dte. |  |  | ORD/003174/2020-2021 | 123/CSD | 29/05/2020 |  | MAA LAXMI ENTERPRISE | 4.61 | 2.3 | 49.88 | 0
72 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special urgent repairing of CI/DI/AC/UPVC Rising main distribution system for damaged due to AMPHAN Cyclone at Canning W/S Scheme under Canning-I&II block & Deuli W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte. |  |  | ORD/003175/2020-2021 | 170/X/AD | 23/05/2020 |  | M/S. TAPAS MONDAL | 9.23 | 4.14 | 44.91 | 0
73 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special urgent repairing of CI/DI/AC/UPVC Rising Main & Distribution System damaged due to AMPHAN cyclone at Budhkhali W/S Scheme under Canning Sub Division of Alipore Division, PHE Dte. |  |  | ORD/003176/2020-2021 | 134/CSD | 01/06/2020 |  | SNIGDHA BUILDERS | 1.34 | 1.34 | 100 | 0
74 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special urgent repairing of CI/DI/AC/UPVC Rising Main & Distribution System damaged due to AMPHAN cyclone at Deuli W/S Scheme under Canning Sub Division of Alipore Division, PHE Dte. |  |  | ORD/003177/2020-2021 | 148/CSD | 04/06/2020 |  | SUJIT KUMAR GHOSH | 1.05 | 1.05 | 100 | 0
75 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special urgent repairing of CI/DI/AC/UPVC Rising Main & Distribution System damaged due to AMPHAN cyclone at Dakshin Rendokhali & Banibadabelekhali W/S Scheme under Canning Sub Division of Alipore Division, PHE Dte. |  |  | ORD/003178/2020-2021 | 170/N/AD | 23/05/2020 |  | TITHI ENTERPRISE | 8.49 | 8.36 | 98.47 | 0
76 | SOUTH 24 PARAGANAS |  | Alipore Division | Temporary Water supply arrangement by different means and Special Repair of damaged existing piped water supply schemes due to Super Cyclone MPHAN' at different blocks of South 24 Parganas District under Alipore Division. | SM/09736 | Disaster | Special urgent repairing of CI/DI/AC/UPVC Rising Main & Distribution System damaged due to AMPHAN cyclone at BHARATGARH W/S Scheme, BLOCK BASANTI under Canning Sub Division of Alipore Division, PHE Dte. |  |  | ORD/003179/2020-2021 | 133/CSD | 01/06/2020 |  | AVIK ENTERPRISE | 0.57 | 0.57 | 100 | 0
Total | [13 empty] | 543.21 | 410.71 | 75.61