## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-I, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/09770 | Retrofitting | Repairing of pump house ? 1 & 3 and approach road and plinth protection at Uttar Kashinagar W/S Scheme, modified as Zone- I of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000993/2023-2024 | 290/RSD | 29/09/2023 | 28/11/2023 | M/S. BISWAS CONSTRUCTION (II) | 3.95 | 3.76 | 95.06 | 100
2 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-I, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/09770 | Retrofitting | Repairing of boundary wall at Head work site of Uttar Kashinagar W/S Scheme, modified as Zone- I of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000994/2023-2024 | 291/RSD | 29/09/2023 | 28/11/2023 | SANKAR HALDER | 4.77 | 4.73 | 99.1 | 100
3 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-I, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/09770 | Retrofitting | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Mathurapur-II, Zone-I (Uttar Kashinagar PWSS) including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Raidighi sub division |  | ORD/001455/2021-2022 | 6070/AD | 17/02/2022 | 17/02/2023 | SPA ENTERPRISE | 117 | 34.65 | 29.62 | 70
4 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-I, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/09770 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000041/2022-2023 | 3582/AD | 29/07/2022 |  | Resource Division | 16.52 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | Alipore Division | Retrofitting of Distribution System of Zone-I, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) & Jal Swapna under Mega Surface Water Based Water Supply Scheme f | SM/09770 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000078/2022-2023 | 5550/AD | 29/09/2022 |  | Resource Division | 4.08 | 0 | 0 | 0
Total | [13 empty] | 146.31 | 43.14 | 29.48