## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Laying distribution system of Nagartala W/S Scheme (Zone-II) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000010/2022-2023 | 65/AD | 06/04/2022 | 04/08/2022 | DIVINE | 245.35 | 245.1 | 99.9 | 100
2 | SOUTH 24 PARAGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Route Survey for Providing FHTC at Ground Water Based Nagartala (Zone-I) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | ORD/001670/2021-2022 | 635/CSD | 10/08/2021 | 25/08/2021 | INDRANIL DUTTA & ASSOCIATES | 4.78 | 2.39 | 49.96 | 100
3 | SOUTH 24 PARAGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Route Survey for Providing FHTC at Ground Water Based Nagartala (Zone-I) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | ORD/001671/2021-2022 | 636/CSD | 10/08/2021 | 25/08/2021 | INDRANIL DUTTA & ASSOCIATES | 4.28 | 3.08 | 71.87 | 100
4 | SOUTH 24 PARAGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Nagartala (Zone-I) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | ORD/001672/2021-2022 | 637/CSD | 10/08/2021 | 25/08/2021 | INDRANIL DUTTA & ASSOCIATES | 3.43 | 3.43 | 100 | 100
5 | SOUTH 24 PARAGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Route Survey for Providing FHTC at Ground Water Based Nagartala (Zone-II) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | ORD/001673/2021-2022 | 638/CSD | 10/08/2021 | 25/08/2021 | INDRANIL DUTTA & ASSOCIATES | 4.64 | 1.95 | 41.99 | 100
6 | SOUTH 24 PARAGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Nagartala (Zone-II) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | ORD/001674/2021-2022 | 639/CSD | 10/08/2021 | 25/08/2021 | INDRANIL DUTTA & ASSOCIATES | 2.67 | 1.34 | 50 | 100
7 | SOUTH 24 PARAGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Route Survey for Providing FHTC at Ground Water Based Nagartala (Zone-II) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | ORD/001675/2021-2022 | 642/CSD | 11/08/2021 | 26/08/2021 | INDRANIL DUTTA & ASSOCIATES | 1.35 | 0.68 | 49.98 | 100
8 | SOUTH 24 PARAGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Nagartala (Zone - II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001678/2022-2023 | 11487/AD | 15/02/2023 | 01/04/2023 | PAL AGENCY | 7.1 | 3.42 | 48.1 | 98
9 | SOUTH 24 PARAGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000068/2022-2023 | 3948/AD | 12/08/2022 |  | Resource Division | 16.35 | 0 | 0 | 0
10 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Supply and installation of 20 KVA servo motor operated copper wound line voltage stabilizer at P.H No. 1, Zone-I of Nagartala w/s Scheme under SMD, PHE. Dte. [Block- Canning-II] |  |  | ORD/002504/2022-2023 | ..550/SMD | 10/06/2022 | 10/07/2022 | DIPALI CONSTRUCTION | 2.69 | 1.32 | 49.18 | 100
Total | [13 empty] | 292.64 | 262.69 | 89.77