## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF KACHUBERIA PWSS FOR FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (PHASE - B) | SM/09997 | Augmentation | Laying distribution system including Functional Household Tap Connection (FHTC) to all households for Augmentation of Kachuberia Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000125/2022-2023 | 2028/AD | 21/06/2022 | 21/07/2022 | M/S. GIRI ENTERPRISE | 12.18 | 12.14 | 99.71 | 20
2 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF KACHUBERIA PWSS FOR FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (PHASE - B) | SM/09997 | Augmentation | Road restoration, Y junction and other allied laying works for providing Functional Household Tap Connection (FHTC) for Kachuberia W/S, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000135/2024-2025 | 2472/AD | 14/06/2024 | 14/07/2024 | SOMBHUNATH BHATTACHARJEE | 6.12 | 2.8 | 45.84 | 100
3 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF KACHUBERIA PWSS FOR FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (PHASE - B) | SM/09997 | Augmentation | Laying distribution system including Functional Household Tap Connection (FHTC) to all households for Augmentation of Kachuberia Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC = 400] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000406/2022-2023 | 4660/AD | 07/09/2022 | 06/12/2022 | SOMBHUNATH BHATTACHARJEE | 111.8 | 111.74 | 99.95 | 100
4 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF KACHUBERIA PWSS FOR FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (PHASE - B) | SM/09997 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KACHUBERIA PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000478/2022-2023 | 297/AD | 12/04/2022 | 27/05/2022 | VOYAGER | 9.73 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF KACHUBERIA PWSS FOR FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (PHASE - B) | SM/09997 | Augmentation | Surging of 1 no. Tubewell for augmentation of Kachuberia W/S Scheme under JJM, Block - Sagar under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000539/2023-2024 | 357/KSD | 09/08/2023 | 29/08/2023 | S.K.GOLUI | 1.77 | 1.77 | 100 | 100
6 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF KACHUBERIA PWSS FOR FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (PHASE - B) | SM/09997 | Augmentation | Construction of 700 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Kachuberia Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001484/2022-2023 | 10710/AD | 02/02/2023 | 29/11/2023 | TARUN KUMAR BHATTACHARYA, PROP.- AVINABA BHATTACHARYA | 992.52 | 355.53 | 35.82 | 51
7 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF KACHUBERIA PWSS FOR FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (PHASE - B) | SM/09997 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Kachuberia PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002055/2022-2023 | 735/KSD | 16/03/2023 | 20/03/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
8 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF KACHUBERIA PWSS FOR FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (PHASE - B) | SM/09997 | Augmentation | Making and fixing of permanent display board at headwork site of Mrityunjoynagar, Radhakrishnapur, Companirchar, Kachuberia PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002168/2023-2024 | 952/KSD | 19/12/2023 | 24/12/2023 | ANANTA KUMAR GIRI | 0.81 | 0.1 | 12.5 | 100
9 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF KACHUBERIA PWSS FOR FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (PHASE - B) | SM/09997 | Augmentation | Carriage of Chlorine from Ganeshpur store to different Pump house of different PWSS of Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (For one year) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002184/2022-2023 | 692/KSD | 23/02/2023 | 23/02/2024 | SUDIP PRADHAN | 2.39 | 1.19 | 50 | 100
10 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF KACHUBERIA PWSS FOR FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (PHASE - B) | SM/09997 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000057/2022-2023 | 3906/AD | 12/08/2022 |  | Resource Division | 117.89 | 0 | 0 | 0
11 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF KACHUBERIA PWSS FOR FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (PHASE - B) | SM/09997 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000282/2023-2024 | 3057/AD | 28/09/2023 |  | Resource Division | 20.5 | 0 | 0 | 0
12 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF KACHUBERIA PWSS FOR FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (PHASE - B) | SM/09997 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000320/2023-2024 | 3135/AD | 29/09/2023 |  | Resource Division | 0.3 | 0 | 0 | 0
13 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF KACHUBERIA PWSS FOR FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (PHASE - B) | SM/09997 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000537/2023-2024 | 21/AD | 02/01/2024 |  | Resource Division | 15.6 | 0 | 0 | 0
14 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF KACHUBERIA PWSS FOR FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (PHASE - B) | SM/09997 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000898/2023-2024 | 884/AD | 07/02/2024 |  | Resource Division | 11.9 | 0 | 0 | 0
15 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KACHUBERIA PWSS FOR FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) (PHASE - B) | SM/09997 | Augmentation | Supply and installation of auto cum manual control panel, pumping machinery, voltage stabilizer, automatic chlorinator and related accessories at PH-2, Zone-I of Kachuberia w/s scheme under SMD, PHE Dte.[Block:Sagar] | Assistant Engineer -I | Junior Engineer | ORD/000075/2022-2023 | 907/SMD | 05/09/2022 | 04/12/2022 | T.S. CONSTRUCTION | 10.48 | 10.41 | 99.37 | 90
Total | [13 empty] | 1314.46 | 496.19 | 37.75