## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED LAKSHMI JANARDANPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/10484 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Laxmi Janardanpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000068/2023-2024 | 49/KSD | 28/04/2023 | 02/05/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
2 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED LAKSHMI JANARDANPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/10484 | Augmentation | Development of Land for sinking of tubewell at 3rd tubewell site of Laxmi Janardanpur W/S scheme under JJM, Block : Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000432/2022-2023 | 205/KSD | 01/06/2022 | 08/06/2022 | AQUATECH ENGINEER | 0.89 | 0.89 | 99.49 | 100
3 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED LAKSHMI JANARDANPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/10484 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Lakshmi Janardhanpur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000464/2022-2023 | 299/AD | 12/04/2022 | 27/05/2022 | INDRANIL DUTTA & ASSOCIATES | 4.77 | 0 | 0 | 100
4 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED LAKSHMI JANARDANPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/10484 | Augmentation | Allied works for pile and pile cap portion regarding the construction of 200 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Laxmi Janardanpur W/S Scheme, South 24 Parganas, Patharpratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000584/2023-2024 | 2438/AD | 22/08/2023 | 06/10/2023 | DEEPAK ENTERPRISE | 31.6 | 15.14 | 47.91 | 100
5 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED LAKSHMI JANARDANPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/10484 | Augmentation | Route Survey for Providing FHTC at Laxmi Janardanpur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001080/2021-2022 | 558/KSD | 08/09/2021 | 28/09/2021 | LEMNISCATE | 4.24 | 4.23 | 99.83 | 100
6 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED LAKSHMI JANARDANPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/10484 | Augmentation | Hiring of Diesel Car / Luxury Taxi for supervision of works of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.08.2022 to 31.01.2023. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001091/2022-2023 | 322/KSD | 26/07/2022 | 26/01/2023 | BADSHA ALOM | 2.4 | 1.86 | 77.8 | 0
7 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED LAKSHMI JANARDANPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/10484 | Augmentation | Route Survey for Providing FHTC at Laxmi Janardanpur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001607/2021-2022 | 605/KSD | 27/09/2021 | 04/10/2021 | LEMNISCATE | 1.55 | 1.51 | 97.27 | 100
8 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED LAKSHMI JANARDANPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/10484 | Augmentation | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for 1 year after completion of FHTC works for Augmentation of Laxmi Janardanpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001649/2022-2023 | 11316/AD | 10/02/2023 | 07/12/2023 | DEEPAK ENTERPRISE | 603.25 | 301.04 | 49.9 | 45
9 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED LAKSHMI JANARDANPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/10484 | Augmentation | Making and fixing of permanent display board at headwork site of Kumarpur, Kedarpur, Purba Dwarokapur, Laxmi Janardanpur, Piprakhali, Dakshin Roypur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002099/2023-2024 | 925/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.95 | 0 | 0 | 100
10 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED LAKSHMI JANARDANPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/10484 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2022-2023 | 3901/AD | 12/08/2022 |  | Resource Division | 10.09 | 0 | 0 | 0
11 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED LAKSHMI JANARDANPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/10484 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000306/2023-2024 | 3101/AD | 28/09/2023 |  | Resource Division | 12.99 | 0 | 0 | 0
12 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED LAKSHMI JANARDANPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/10484 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000314/2023-2024 | 3123/AD | 29/09/2023 |  | Resource Division | 0.3 | 0 | 0 | 0
13 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED LAKSHMI JANARDANPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/10484 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000569/2023-2024 | 78/AD | 03/01/2024 |  | Resource Division | 14.52 | 0 | 0 | 0
14 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED LAKSHMI JANARDANPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/10484 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00015/2023-2024 | BP-2023-24-47 | 18/05/2023 |  | WBSEDCL | 3.74 | 0 | 0 | 0
15 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED LAKSHMI JANARDANPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRICT | SM/10484 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 3 of Laxmi Janardanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I | Junior Engineer | ORD/000058/2023-2024 | 1226/SMD | 04/05/2023 | 02/08/2023 | J.K. ENGINEERING CO. | 10.86 | 10.21 | 94 | 0
Total | [13 empty] | 702.63 | 335.37 | 47.73