## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Sumatinagar Zone-II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000078/2023-2024 | 62/KSD | 02/05/2023 | 06/05/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
2 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Construction of Household Tap Platform at different household etc. for Augmentation of Sumatinagar (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) (SM/13569) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000152/2024-2025 | 2490/AD | 14/06/2024 | 28/08/2024 | COPE ENTERPRISE | 57.99 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Construction of Household Tap Platform at different household etc. for Augmentation of Sumatinagar (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) (SM/13569) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000153/2024-2025 | 2491/AD | 14/06/2024 | 14/07/2024 | ANANTA KUMAR GIRI | 26.9 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Construction of Household Tap Platform at different household etc. for Augmentation of Sumatinagar (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) (SM/13569) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000154/2024-2025 | 2492/AD | 14/06/2024 | 14/07/2024 | FIDERE MARINE SERVICES PVT. LTD. | 6.12 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Allied works for pile and pile cap portion regarding the construction of 250 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Sumatinagar (Zone-I & II), South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000281/2023-2024 | 1431/AD | 13/07/2023 | 27/08/2023 | GROWING CONCERN | 41.85 | 17.33 | 41.4 | 100
6 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell Replacement Tubewell (damaged due to natural calamities) by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st Tubewell Site for Augmentation of Sumatinagar (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000420/2023-2024 | 1909/AD | 01/08/2023 | 31/08/2023 | SARADA CONSTRUCTION | 24.12 | 23.31 | 96.62 | 100
7 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Laying distribution system for providing FHTC for Augmentation of Sumatinagar (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part - F) (SM/13569) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000495/2024-2025 | 3571/AD | 04/09/2024 | 03/12/2024 | GROWING CONCERN | 100.89 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Supplying, fitting, fixing and delivery of different dia. specials for Augmentation of Sumatinagar (Zone-I and II) W/S Scheme under JJM, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000720/2023-2024 | 2537/AD | 28/08/2023 | 27/09/2023 | ANANTA KUMAR GIRI | 8.71 | 4.36 | 50 | 100
9 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Sumatinagar (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000774/2022-2023 | 6646/AD | 14/11/2022 | 29/12/2022 | SARADA CONSTRUCTION | 45.89 | 27.91 | 60.82 | 100
10 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Sumatinagar (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000775/2022-2023 | 6647/AD | 14/11/2022 | 14/12/2022 | FIDERE MARINE SERVICES PVT. LTD. | 12.01 | 9.34 | 77.75 | 100
11 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Sumatinagar (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000777/2022-2023 | 6648/AD | 14/11/2022 | 29/11/2022 | RANJIT CONSTRUCTION | 7.99 | 2.31 | 28.95 | 100
12 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Sumatinagar (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC =835] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000813/2022-2023 | 6754/AD | 15/11/2022 | 15/03/2023 | UCON | 140.93 | 102.93 | 73.04 | 100
13 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Development of Land for sinking of 02 nos. tubewell for Sumatinagar Zone - II W/S scheme under JJM, Block : Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000989/2023-2024 | 504/KSD | 03/10/2023 | 10/10/2023 | SARADA CONSTRUCTION | 2.57 | 1.27 | 49.46 | 100
14 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (SUMATINAGAR (ZONE - I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001057/2022-2023 | 4648/AD | 06/09/2022 | 21/10/2022 | VOYAGER | 8.14 | 8.14 | 100 | 100
15 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with 2 nos. Pump House and Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Sumatinagar (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001063/2022-2023 | 8204/AD | 06/12/2022 | 02/10/2023 | GROWING CONCERN | 509.34 | 390.88 | 76.74 | 88
16 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Making and fixing of permanent display board at headwork site of Mahishamari Zone - I & II, Sumatinagar Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002153/2023-2024 | 948/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.81 | 0.2 | 24.99 | 100
17 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Sumatinagar (Zone-I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002176/2023-2024 | 813/AD | 05/02/2024 | 06/03/2024 | M/S. MA BHABANI CONSTRUCTION | 11.71 | 5.12 | 43.68 | 100
18 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Sumatinagar (Zone-I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002467/2023-2024 | 1571/AD | 16/03/2024 | 30/04/2024 | BIMALENDU GIRI | 33.73 | 0 | 0 | 0
19 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000498/2023-2024 | 4824/AD | 20/12/2023 |  | Resource Division | 34.63 | 0 | 0 | 0
20 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000542/2023-2024 | 26/AD | 02/01/2024 |  | Resource Division | 10.31 | 0 | 0 | 0
21 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000965/2023-2024 | 1758/AD | 27/03/2024 |  | Resource Division | 28.55 | 0 | 0 | 0
22 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00016/2023-2024 | BP-2023-24-34 | 18/05/2023 |  | WBSEDCL | 5.87 | 0 | 0 | 0
23 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION FOR GROUND WATER BASED SUMATINAGAR (ZONE - I & II) PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13569 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I & II for Augmentation of Sumatinagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I | Junior Engineer | ORD/000341/2022-2023 | 3745/SMD | 29/12/2022 | 29/03/2023 | RELIABLE CONSTRUCTION | 20.25 | 9.19 | 45.4 | 0
Total | [13 empty] | 1139.8 | 602.77 | 52.88