## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM DUE TO IMPROVEMENT OF WATER BY INTER CONNECTION FROM EXISTING TUBEWELLS WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-IV OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER B | SM/13914 | Augmentation | Repairing and Renovation of existing 100 Cum. capacity Over Head Reservoir of Zone-IV, Diamond Harbour -II Block (At Sarisha Ramkrishna Mission) Water Supply Scheme under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000131/2023-2024 | 490/AD | 10/05/2023 | 09/07/2023 | NIVA CONSTRUCTION | 20.82 | 0 | 0 | 100
2 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM DUE TO IMPROVEMENT OF WATER BY INTER CONNECTION FROM EXISTING TUBEWELLS WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-IV OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER B | SM/13914 | Augmentation | Earnest money credit | Assistant Engineer, Diamond Harbour sub division |  | ORD/001536/2017-2018 | 2719/AD | 17/11/2017 |  | ALOK ENTERPRISE | 218 | 0.1 | 0.04 | 0
3 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM DUE TO IMPROVEMENT OF WATER BY INTER CONNECTION FROM EXISTING TUBEWELLS WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-IV OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER B | SM/13914 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000142/2022-2023 | 15/AD | 05/04/2023 |  | Resource Division | 15.11 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM DUE TO IMPROVEMENT OF WATER BY INTER CONNECTION FROM EXISTING TUBEWELLS WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-IV OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER B | SM/13914 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000182/2023-2024 | 1273/AD | 05/07/2023 |  | Resource Division | 15.11 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM DUE TO IMPROVEMENT OF WATER BY INTER CONNECTION FROM EXISTING TUBEWELLS WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-IV OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER B | SM/13914 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000353/2023-2024 | 3217/AD | 04/10/2023 |  | Resource Division | 0.21 | 0 | 0 | 0
Total | [13 empty] | 269.25 | 0.1 | 0.04