## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM DUE TO IMPROVEMENT OF WATER BY INTER CONNECTION FROM EXISTING TUBEWELLS WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-V OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER BA | SM/13915 | Augmentation | Interconnection of tubewell, and erection of RBT fencing at Pump House No.-2 of Khandalia W/S Scheme, Block: Diamond Harbour-II under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000822/2022-2023 | 206/DHSD | 02/08/2022 | 16/09/2022 | S.S. ENTERPRISE (II) | 2.66 | 0 | 0 | 100
2 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM DUE TO IMPROVEMENT OF WATER BY INTER CONNECTION FROM EXISTING TUBEWELLS WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-V OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER BA | SM/13915 | Augmentation | Construction of Boundary wall,approach road and renovation of Pump House as per departmental design and drawing at Pump House No. 2 of Khandalia W/S Scheme under Diamond Harbour Sub-Division of Alipore Division, P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001520/2020-2021 | 336/DHSD | 06/01/2021 | 05/02/2021 | M/S. SUMAN ENTERPRISE | 4.81 | 0 | 0 | 100
3 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM DUE TO IMPROVEMENT OF WATER BY INTER CONNECTION FROM EXISTING TUBEWELLS WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-V OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER BA | SM/13915 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000355/2023-2024 | 3219/AD | 04/10/2023 |  | Resource Division | 0.21 | 0 | 0 | 0
Total | [13 empty] | 7.68 | 0 | 0