## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM DUE TO IMPROVEMENT OF WATER BY INTER CONNECTION FROM EXISTING TUBEWELLS WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-VI OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER B | SM/13916 | Augmentation | Laying of distribution system at Zone-VI of Diamond Harbour-II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000564/2021-2022 | 2702/AD | 01/10/2021 | 30/03/2022 | MALAY KANTI DEY | 125.75 | 58.66 | 46.64 | 47
2 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM DUE TO IMPROVEMENT OF WATER BY INTER CONNECTION FROM EXISTING TUBEWELLS WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-VI OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER B | SM/13916 | Augmentation | Functional Household Tap Connection (FHTC) for balance portion in Diamond Harbour-II Zone-VI (Khordanahala) for providing 100% coverage for Swajal Gram activity under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas, Block Falta, under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000750/2022-2023 | 6181/AD | 01/11/2022 | 01/12/2022 | ADITYA HAZRA | 46.66 | 44.47 | 95.31 | 65
Total | [13 empty] | 172.41 | 103.13 | 59.81