## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | GROUND WATER BASED NADABANGHA PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14158 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Nadabhanga W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000133/2024-2025 | 2470/AD | 14/06/2024 | 29/07/2024 | M/S MAITY CONSTRUCTION | 27.83 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | GROUND WATER BASED NADABANGHA PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14158 | New | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc. for Nadabangha W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14158) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000404/2024-2025 | 3187/AD | 31/07/2024 | 14/10/2024 | UCON (II) | 95.23 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | GROUND WATER BASED NADABANGHA PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14158 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Nadabangha W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001305/2022-2023 | 9888/AD | 10/01/2023 | 24/02/2023 | MONDAL ENTERPRISE (MURSHIDABAD) | 38.59 | 34.36 | 89.04 | 0
4 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | GROUND WATER BASED NADABANGHA PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14158 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Nadabhanga PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001798/2022-2023 | 3695/AD | 02/08/2022 | 16/09/2022 | M/S R.DUTTA & CO. | 7.26 | 7.26 | 100 | 95
5 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | GROUND WATER BASED NADABANGHA PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14158 | New | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Nadabangha Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 2365] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002081/2022-2023 | 12546/AD | 10/03/2023 | 04/01/2024 | UCON | 385.79 | 34.81 | 9.02 | 20
6 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | GROUND WATER BASED NADABANGHA PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14158 | New | Making and fixing of permanent display board at headwork site of Nadabhanga, Patibania, Dakshin Durgapur, Rajnagar, Budhakhali Zone - I (Part - I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002128/2023-2024 | 935/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.95 | 0 | 0 | 90
7 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | GROUND WATER BASED NADABANGHA PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14158 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of 250 cum. capacity OHR of Nadabhanga PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002215/2023-2024 | 872/KSD | 14/12/2023 | 19/12/2023 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0.24 | 50 | 100
8 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | GROUND WATER BASED NADABANGHA PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14158 | New | Material Requisition To Resource Division |  |  | RTOR000479/2023-2024 | 4783/AD | 19/12/2023 |  | Resource Division | 16.42 | 0 | 0 | 0
9 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | GROUND WATER BASED NADABANGHA PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14158 | New | Material Requisition To Resource Division |  |  | RTOR000556/2023-2024 | 44/AD | 03/01/2024 |  | Resource Division | 14.05 | 0 | 0 | 0
10 | SOUTH 24 PARAGANAS | Namkhana | S24 Pgns Mechanical | GROUND WATER BASED NADABANGHA PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14158 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01116/2023-2024 | BP-2023-24-157 | 24/07/2023 |  | WBSEDCL | 6.71 | 0 | 0 | 0
11 | SOUTH 24 PARAGANAS | Namkhana | S24 Pgns Mechanical | GROUND WATER BASED NADABANGHA PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14158 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01715/2023-2024 | BP-2023-24-194 | 09/08/2023 |  | WBSEDCL | 8.4 | 0 | 0 | 0
12 | SOUTH 24 PARAGANAS | Namkhana | S24 Pgns Mechanical | GROUND WATER BASED NADABANGHA PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14158 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Nadabhanga water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000426/2022-2023 | 3822/SMD | 29/12/2022 | 29/03/2023 | S.K. ENTERPRISE | 22.69 | 10.25 | 45.17 | 90
Total | [13 empty] | 624.4 | 86.92 | 13.92