## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC UNDER ZONE- IIIB (DOSTIPUR) OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTR | SM/14465 | Augmentation | Augmentation of laying distribution system with allied works to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-III B (Dostipur) at Falta block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-2330]. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000306/2023-2024 | 1509/AD | 15/07/2023 | 12/11/2023 | M/S A.K. GHATAK | 455.49 | 108.83 | 23.89 | 70
2 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC UNDER ZONE- IIIB (DOSTIPUR) OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTR | SM/14465 | Augmentation | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone- III(B) (Dostipur) of Falta Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/001000/2022-2023 | 288/DHSD | 15/09/2022 | 15/10/2022 | GEO SOLUTION | 2.83 | 2.71 | 95.92 | 0
3 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC UNDER ZONE- IIIB (DOSTIPUR) OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTR | SM/14465 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000137/2022-2023 | 20/AD | 05/04/2023 |  | Resource Division | 12.74 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC UNDER ZONE- IIIB (DOSTIPUR) OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTR | SM/14465 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000184/2023-2024 | 1278/AD | 05/07/2023 |  | Resource Division | 12.74 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC UNDER ZONE- IIIB (DOSTIPUR) OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTR | SM/14465 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000428/2023-2024 | 3622/AD | 30/10/2023 |  | Resource Division | 14.35 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC UNDER ZONE- IIIB (DOSTIPUR) OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTR | SM/14465 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000621/2023-2024 | 282/AD | 15/01/2024 |  | Resource Division | 0.79 | 0 | 0 | 0
Total | [13 empty] | 498.93 | 111.54 | 22.36