## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRIDHARNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14986 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Sridharnagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone - II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000157/2023-2024 | 679/AD | 17/05/2023 | 16/06/2023 | M/S S.DAS ENTERPRISE | 11.79 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRIDHARNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14986 | Augmentation | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile and pile cap for OHR etc. at Sridharnagar (Zone-I & II) PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14986) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000362/2024-2025 | 2891/AD | 09/07/2024 | 07/10/2024 | TANMAY ROY CHOWDHURY | 261.1 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRIDHARNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14986 | Augmentation | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Sridharnagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone-II) (2nd Call) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000918/2023-2024 | 2971/AD | 26/09/2023 | 10/11/2023 | ARBINA ENTERPRISE | 34.35 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRIDHARNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14986 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Sridharnagar PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Patharpratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001792/2022-2023 | 3958/AD | 12/08/2022 | 26/09/2022 | INDRANIL DUTTA & ASSOCIATES | 6.64 | 6.64 | 100 | 95
5 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRIDHARNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14986 | Augmentation | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Sridharnagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001963/2023-2024 | 397AD | 22/01/2024 | 07/03/2024 | AQUATECH ENGINEERS | 49.26 | 24.57 | 49.88 | 100
6 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRIDHARNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14986 | Augmentation | Construction of 150 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Sridharnagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) [No. of FHTC = 100 ] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002026/2022-2023 | 12993/AD | 23/03/2023 | 17/01/2024 | TANMAY ROY CHOWDHURY | 296.12 | 0 | 0 | 5
7 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRIDHARNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14986 | Augmentation | Construction of 150 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Sridharnagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 100 ] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002027/2022-2023 | 12994/AD | 23/03/2023 | 17/01/2024 | TANMAY ROY CHOWDHURY | 290.89 | 0 | 0 | 5
8 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRIDHARNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14986 | Augmentation | Making and fixing of permanent display board at headwork site of Sridharnagar Zone - I & II, Rakhalpur Zone - I & II PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002106/2023-2024 | 928/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.81 | 0 | 0 | 100
9 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRIDHARNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14986 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Sridharnagar Zone - I & II PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002604/2023-2024 | 290/KSD | 07/02/2024 | 12/02/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
10 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRIDHARNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14986 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Sridharnagar (Zone - I & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002609/2023-2024 | 304/KSD | 08/02/2024 | 13/02/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
11 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRIDHARNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14986 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000446/2023-2024 | 4766/AD | 19/12/2023 |  | Resource Division | 38.86 | 0 | 0 | 0
12 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRIDHARNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14986 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000564/2023-2024 | 83/AD | 03/01/2024 |  | Resource Division | 0.59 | 0 | 0 | 0
13 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRIDHARNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14986 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000762/2023-2024 | 596/AD | 29/01/2024 |  | Resource Division | 6.76 | 0 | 0 | 0
14 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRIDHARNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14986 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000963/2023-2024 | 1697/AD | 22/03/2024 |  | Resource Division | 11.88 | 0 | 0 | 0
15 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED SRIDHARNAGAR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14986 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,&2 for Augmentation of Sridharnagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I | Junior Engineer | ORD/000800/2022-2023 | 772/SMD | 16/03/2023 | 14/06/2023 | S.G.TECHNICAL SERVICES | 22.15 | 0 | 0 | 0
Total | [13 empty] | 1032.17 | 32.18 | 3.12