## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-I) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000108/2023-2024 | 506/AD | 11/05/2023 | 26/05/2023 | A.P. CONSTRUCTION | 13.02 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Construction of OHR, Laying of Distribution System, Providing Functional Household Tap Connection of Augmentation Piped Water Supply Scheme for Basanti (Zone-I, II, IV, V & VI), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No of FHTC=9052] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000349/2023-2024 | 1659/AD | 20/07/2023 | 15/05/2024 | M/S PATH MAKERS | 2061.38 | 0 | 0 | 35
3 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Supply of water through pipe line connection at BL & LRO Basanti office from existing pipe line of Basanti W/S Scheme (Zone-I), Block - Basanti, under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001196/2020-2021 | 1180/CSD | 15/12/2020 | 22/12/2020 | A.P. CONSTRUCTION | 0.65 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Inter connection in between the replacement tubewell towards distribution system for Basanti W/S Scheme (Zone-I), Block - Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (TW-1) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001261/2023-2024 | 1205/CSD | 10/11/2023 | 10/12/2023 | SUSHANTA MANDAL | 1.06 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Basanti (Zone-I) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001349/2022-2023 | 10216/AD | 19/01/2023 | 20/03/2023 | SNEHA CONSTRUCTION | 58.47 | 10.92 | 18.68 | 36
6 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Pipe line connection from Petrol Pump of Rambabu to basanti Chowmatha TV Relay Centre at Basanti W/S Scheme (Zone-I), Block - Basanti, under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001397/2023-2024 | 1129/CSD | 30/10/2023 | 29/11/2023 | KAYAL ENTERPRISE | 1.62 | 0.81 | 49.83 | 100
7 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-I), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001700/2022-2023 | 11664/AD | 20/02/2023 | 06/04/2023 | LASKAR CONSTRUCTION | 7.24 | 3.52 | 48.62 | 98
8 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-I) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001701/2022-2023 | 11665/AD | 20/02/2023 | 06/04/2023 | SUJOY SADHUKHAN | 7.08 | 0 | 0 | 0
9 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-I) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001702/2022-2023 | 11666/AD | 20/02/2023 | 06/04/2023 | SARKAR CONSTRUCTION | 7.11 | 0 | 0 | 0
10 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001915/2022-2023 | 10941/AD | 06/02/2023 | 23/03/2023 | INDRANIL DUTTA & ASSOCIATES | 7.25 | 7.25 | 100 | 99
11 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2023-2024 | 227/AD | 24/04/2023 |  | Resource Division | 110.78 | 0 | 0 | 0
12 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000150/2023-2024 | 1053/AD | 15/06/2023 |  | Resource Division | 16.16 | 0 | 0 | 0
13 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000250/2023-2024 | 3042/AD | 28/09/2023 |  | Resource Division | 94.19 | 0 | 0 | 0
14 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Charges for service connection at Pump house no- 2 of Basanti Aug (Z-I) |  |  | BILL/00444/2024-2025 | BP-2024-25-113 | 14/06/2024 |  | WBSEDCL | 10.42 | 0 | 0 | null
15 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Basanti (Zone-1) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/000021/2023-2024 | 956/SMD | 04/04/2023 | 03/07/2023 | M/S. S.R. ENTERPRISE | 29.05 | 0 | 0 | 0
16 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF BASANTI (ZONE-I) PWSS FOR PROVIDING FHTC, BLOCK - BASANTI | SM/15053 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, for Augmentation of Basanti Zone-I water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/000490/2022-2023 | 292/SMD | 03/02/2023 | 04/05/2023 | SRI KRISHNA NIRMAN | 11.69 | 0 | 0 | 0
Total | [13 empty] | 2437.15 | 22.5 | 0.92