## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF NAGARTALA (ZONE - I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15081 | Augmentation | Laying distribution system of Nagartala W/S Scheme (Zone-I) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000117/2022-2023 | 1662/AD | 10/06/2022 | 08/10/2022 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 369.02 | 140.06 | 37.96 | 20
2 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF NAGARTALA (ZONE - I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15081 | Augmentation | Sinking of 04 (four) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New & Replacement) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Nagartala (Zone - I &II) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001661/2022-2023 | 11474/AD | 15/02/2023 | 16/05/2023 | MERAJUL ALAM | 78.41 | 48.81 | 62.24 | 35
3 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF NAGARTALA (ZONE - I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15081 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Nagartala (Zone - I) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001676/2022-2023 | 11485/AD | 15/02/2023 | 01/04/2023 | SAHANA ENTERPRISE | 7.07 | 3.41 | 48.23 | 100
4 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF NAGARTALA (ZONE - I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15081 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Nagartala (Zone - II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 3) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001677/2022-2023 | 11486/AD | 15/02/2023 | 01/04/2023 | SAHANA ENTERPRISE | 7.06 | 3.4 | 48.19 | 100
5 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF NAGARTALA (ZONE - I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15081 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Nagartala (Zone - II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001679/2022-2023 | 11488/AD | 15/02/2023 | 01/04/2023 | PAL AGENCY | 7.1 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF NAGARTALA (ZONE - I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15081 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 115/AD | 13/04/2023 |  | Resource Division | 0.34 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF NAGARTALA (ZONE - I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15081 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000135/2023-2024 | 842/AD | 27/05/2023 |  | Resource Division | 1.72 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF NAGARTALA (ZONE - I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15081 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000255/2023-2024 | 3047/AD | 28/09/2023 |  | Resource Division | 232.42 | 0 | 0 | 0
9 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF NAGARTALA (ZONE - I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15081 | Augmentation | Quotation for new service( power) connection at Nagartala Zone-II PH-4 Water supply scheme under Canning-II block. Reference ID:-106599060, Application No :-1007776063 |  |  | BILL/00378/2024-2025 | BP-2024-25-88 | 05/06/2024 |  | WBSEDCL | 3.69 | 0 | 0 | null
10 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF NAGARTALA (ZONE - I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15081 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03522/2023-2024 | BP-2023-24-386 | 23/11/2023 |  | WBSEDCL | 22.27 | 0 | 0 | 0
11 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF NAGARTALA (ZONE - I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15081 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04078/2023-2024 | BP-2023-24-424 | 18/12/2023 |  | WBSEDCL | 3.69 | 0 | 0 | 0
12 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF NAGARTALA (ZONE - I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15081 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/06256/2023-2024 | BP-2023-24-643 | 29/03/2024 |  | WBSEDCL | 13.27 | 0 | 0 | 0
13 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF NAGARTALA (ZONE - I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15081 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 & 2 for Augmentation of Nagartala (Zone-1 & 2) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000041/2023-2024 | 1002/SMD | 10/04/2023 | 09/07/2023 | ESENCE ENGINEERING CONCERN | 21.57 | 10.15 | 47.06 | 90
14 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF NAGARTALA (ZONE - I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15081 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Augmentation of Nagartala Zone-I and II Piped water supply scheme under SMD, PHE Dte. Block Canning-II | Assistant Engineer | Junior Engineer | ORD/001913/2023-2024 | 1195/SMD | 22/03/2024 | 20/06/2024 | ROY & BISWAS ENGG. CO. | 12.99 | 0 | 0 | 0
15 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF NAGARTALA (ZONE - I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15081 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 2 of Augmentation of Nagartala Zone-I and II Piped water supply scheme under SMD, PHE Dte. Block Canning-II | Assistant Engineer | Junior Engineer | ORD/001915/2023-2024 | 1196/SMD | 22/03/2024 | 20/06/2024 | M/S.UTTAM KUMAR CHATTERJEE | 12.99 | 0 | 0 | 0
16 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF NAGARTALA (ZONE - I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15081 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Augmentation of Nagartala Zone-II PH-2, under Canning-II Block water supply sche under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002811/2023-2024 | 192/SMSD | 09/02/2024 | 24/02/2024 | ESENCE ENGINEERING CONCERN | 0.88 | 0 | 0 | 0
17 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF NAGARTALA (ZONE - I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15081 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Augmentation of Nagartala Zone-I PH-1, under Canning-II Block water supply sche under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002812/2023-2024 | 186/SMSD | 08/02/2024 | 23/02/2024 | ESENCE ENGINEERING CONCERN | 0.88 | 0 | 0 | 0
Total | [13 empty] | 795.38 | 205.83 | 25.88